## P1_Constrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 18-09-2023 | 18-09-2023 | 0 | 0 |  | 3
3 | Pre-Construction | Project planning | 30 | 18-09-2023 | 27-10-2023 | 0 | 30 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 150 | 30-10-2023 | 24-05-2024 | 30 | 180 | 3 | 56
5 | Pre-Construction | Conceptual design | 5 | 30-10-2023 | 03-11-2023 | 30 | 35 | 3 | 6
6 | Pre-Construction | Functional requirements definition | 5 | 19-02-2024 | 23-02-2024 | 110 | 115 | 5 | 7; 8; 9
7 | Pre-Construction | Zone 1 design | 8 | 07-03-2024 | 18-03-2024 | 123 | 131 | 6 | 10; 11; 12; 13; 14
8 | Pre-Construction | Zone 2 design | 8 | 19-03-2024 | 28-03-2024 | 131 | 139 | 6 | 10; 11; 12; 13; 29
9 | Pre-Construction | Zone 3 design | 8 | 29-03-2024 | 09-04-2024 | 139 | 147 | 6 | 10; 11; 12; 13
10 | Pre-Construction | Construction tramits | 30 | 10-04-2024 | 21-05-2024 | 147 | 177 | 7; 8; 9 | 14; 29; 54
11 | Pre-Construction | Operations licenses | 25 | 10-04-2024 | 14-05-2024 | 147 | 172 | 7; 8; 9 | 54
12 | Pre-Construction | Insurance contract | 9 | 15-05-2024 | 27-05-2024 | 172 | 181 | 7; 8; 9 | 54
13 | Pre-Construction | Bidding | 15 | 10-04-2024 | 30-04-2024 | 147 | 162 | 7; 8; 9 | 14; 15; 16; 29; 30; 31; 42; 43; 41
14 | Construction | Pipeline system zone 1 | 7 | 23-01-2025 | 31-01-2025 | 353 | 360 | 7; 10; 13; P2-9; P3-8 | 15; 23
15 | Construction | Electrical system zone 1 | 10 | 03-02-2025 | 14-02-2025 | 360 | 370 | 13; 14 | 17; 18; 19; 20; 21; 16
16 | Construction | Air Condition System zone 1 | 5 | 17-02-2025 | 21-02-2025 | 370 | 375 | 13; 15 | 17
17 | Construction | Floor adaptation zone 1 | 3 | 24-02-2025 | 26-02-2025 | 375 | 378 | 15; 16 | 18
18 | Construction | Installation of mirrors | 2 | 27-02-2025 | 28-02-2025 | 378 | 380 | 15; 17 | 19
19 | Construction | Replacement of toilets zone 1 | 5 | 03-03-2025 | 07-03-2025 | 380 | 385 | 15; 18 | 25
20 | Construction | Installation of stair | 7 | 17-02-2025 | 25-02-2025 | 370 | 377 | 15 | 21
21 | Construction | Elevator replacement | 7 | 26-02-2025 | 06-03-2025 | 377 | 384 | 15; 20 | 22
22 | Construction | Installation of turnstiles for employee entry | 2 | 07-03-2025 | 10-03-2025 | 384 | 386 | 21 | 23
23 | Construction | Installation of fiber optics for WiFi zone 1 | 1 | 11-03-2025 | 11-03-2025 | 386 | 387 | 22; 14 | 24
24 | Construction | Installation of water dispensers | 1 | 12-03-2025 | 12-03-2025 | 387 | 388 | 23 | 25
25 | Construction | Wall patching on floor 1 | 8 | 13-03-2025 | 24-03-2025 | 388 | 396 | 24; 19 | 26FC+5
26 | Construction | Painting walls on floor 1 | 5 | 01-04-2025 | 07-04-2025 | 401 | 406 | 25FC+5 | 27; 28
27 | Construction | Adaptation and installation of machinary | 6 | 08-04-2025 | 15-04-2025 | 406 | 412 | 26 | 28
28 | Construction | Furniture installation | 2 | 16-04-2025 | 17-04-2025 | 412 | 414 | 26; 27 | 53
29 | Construction | Pipeline system zone 2 | 6 | 22-05-2024 | 29-05-2024 | 177 | 183 | 8; 10; 13 | 30
30 | Construction | Electrical system zone 2 | 9 | 30-05-2024 | 11-06-2024 | 183 | 192 | 13; 29 | 32; 31; 33
31 | Construction | Air Condition System zone 2 | 5 | 12-06-2024 | 18-06-2024 | 192 | 197 | 13; 30 | 32
32 | Construction | Floor adaptation zone 2 | 3 | 19-06-2024 | 21-06-2024 | 197 | 200 | 30; 31 | 34; 35; 36FC+8
33 | Construction | Installation electrical stair | 14 | 12-06-2024 | 01-07-2024 | 192 | 206 | 30 | 35
34 | Construction | Replacement of toilets zone 2 | 8 | 24-06-2024 | 03-07-2024 | 200 | 208 | 32 | 35
35 | Construction | Elevator door adaptation | 3 | 04-07-2024 | 08-07-2024 | 208 | 211 | 34; 32; 33 | 37
36 | Construction | Installation of fiber optics for WiFi zone 2 | 3 | 04-07-2024 | 08-07-2024 | 208 | 211 | 32FC+8 | 37
37 | Construction | Wall patching on floor zone 2 | 8 | 09-07-2024 | 18-07-2024 | 211 | 219 | 36; 35 | 38FC+5
38 | Construction | Painting walls on floor zone 2 | 5 | 26-07-2024 | 01-08-2024 | 224 | 229 | 37FC+5 | 39; 40
39 | Construction | Nurses room adaptation | 3 | 02-08-2024 | 06-08-2024 | 229 | 232 | 38 | 53
40 | Construction | Medical consultancy rooms | 8 | 02-08-2024 | 13-08-2024 | 229 | 237 | 38 | 41; 53
41 | Construction | Pipeline system zone 3 | 6 | 14-08-2024 | 21-08-2024 | 237 | 243 | 40; 13 | 42; 46; 47
42 | Construction | Electrical system zone 3 | 9 | 22-08-2024 | 03-09-2024 | 243 | 252 | 13; 41 | 43; 45FC+5; 47
43 | Construction | Air Condition System zone 3 | 5 | 04-09-2024 | 10-09-2024 | 252 | 257 | 13; 42 | 44
44 | Construction | Replacement of toilets zone 3 | 3 | 11-09-2024 | 13-09-2024 | 257 | 260 | 43 | 46
45 | Construction | Elevator door adaptation | 2 | 11-09-2024 | 12-09-2024 | 257 | 259 | 42FC+5 | 48
46 | Construction | Installation of fiber optics for WiFi zone 3 | 2 | 16-09-2024 | 17-09-2024 | 260 | 262 | 41; 44 | 48
47 | Construction | Industrial kitchen installment | 10 | 04-09-2024 | 17-09-2024 | 252 | 262 | 41; 42 | 48
48 | Construction | Wall patching on floor zone 3 | 8 | 18-09-2024 | 27-09-2024 | 262 | 270 | 46; 45; 47 | 49FC+5
49 | Construction | Painting walls on floor zone 3 | 5 | 07-10-2024 | 11-10-2024 | 275 | 280 | 48FC+5 | 50; 51; 52FC+2
50 | Construction | Clients room adaptation | 3 | 14-10-2024 | 16-10-2024 | 280 | 283 | 49 | 53
51 | Construction | Dining room adaptation | 3 | 14-10-2024 | 16-10-2024 | 280 | 283 | 49 | 53
52 | Construction | Control Center installment | 1 | 16-10-2024 | 16-10-2024 | 282 | 283 | 49FC+2 | 53
53 | Construction | Equipment functionality test | 3 | 21-05-2026 | 25-05-2026 | 698 | 701 | 28; 40; 52; 39; 50; 51 | 54
54 | Construction | Final test supporting document | 1 | 26-05-2026 | 26-05-2026 | 701 | 702 | 10; 11; 12; 53 | 55
55 | Construction | Operations manual | 1 | 27-05-2026 | 27-05-2026 | 702 | 703 | 54 | 56
56 | Post-Contruction | Contracts closure | 3 | 28-05-2026 | 01-06-2026 | 703 | 706 | 4; 55 | 57
57 | Post-Contruction | Project closing report | 1 | 02-06-2026 | 02-06-2026 | 706 | 707 | 56 | 58
58 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 03-06-2026 | 03-06-2026 | 707 | 707 | 57

## P2_Constrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 25-09-2023 | 25-09-2023 | 5 | 5 |  | 3
3 | Pre-Construction | Project planning | 60 | 25-09-2023 | 15-12-2023 | 5 | 65 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 500 | 18-12-2023 | 14-11-2025 | 65 | 565 | 3 | 33
5 | Pre-Construction | Documentation analysis | 30 | 18-12-2023 | 26-01-2024 | 65 | 95 | 3 | 6
6 | Pre-Construction | Consultation results report | 30 | 29-01-2024 | 08-03-2024 | 95 | 125 | 5 | 7; 8FC+5
7 | Pre-Construction | Architectural design | 20 | 11-03-2024 | 05-04-2024 | 125 | 145 | 6 | 9
8 | Pre-Construction | Lanscape design | 15 | 08-04-2024 | 26-04-2024 | 145 | 160 | 6FC+5 | 9
9 | Pre-Construction | Final design | 20 | 09-05-2024 | 05-06-2024 | 168 | 188 | 7; 8 | 10; 11; 12; 13FC+20; 14FC+35; 15
10 | Pre-Construction | Legal permits | 30 | 06-06-2024 | 17-07-2024 | 188 | 218 | 9 | 16
11 | Pre-Construction | Environmental permits | 30 | 18-07-2024 | 28-08-2024 | 218 | 248 | 9 | 16
12 | Pre-Construction | Construction license | 30 | 29-08-2024 | 09-10-2024 | 248 | 278 | 9 | 16
13 | Pre-Construction | Providers contracts | 45 | 04-07-2024 | 04-09-2024 | 208 | 253 | 9FC+20 | 17; 18; 19; 20; 21; 22; 23; 24; 25; 26
14 | Pre-Construction | Components contracts | 30 | 05-09-2024 | 16-10-2024 | 253 | 283 | 9FC+35 | 27; 28; 29
15 | Pre-Construction | Procurement documents | 70 | 17-10-2024 | 22-01-2025 | 283 | 353 | 9 | 16; 17; 18; 19; 20; 21; 22; 23; 24; 25; 26; 27; 28; 29
16 | Construction | Site preparation | 25 | 23-01-2025 | 26-02-2025 | 353 | 378 | 10; 11; 12; 15; P1-7; P1-8; P1-9; P3-8 | 17
17 | Construction | Sanitary Water system | 18 | 27-02-2025 | 24-03-2025 | 378 | 396 | 13; 15; 16 | 18
18 | Construction | Electrical system | 43 | 25-03-2025 | 22-05-2025 | 396 | 439 | 13; 15; 17 | 19; 20
19 | Construction | Soccer field | 36 | 23-05-2025 | 11-07-2025 | 439 | 475 | 13; 15; 18 | 20
20 | Construction | Changing rooms & toilettes | 39 | 14-07-2025 | 04-09-2025 | 475 | 514 | 13; 15; 18; 19 | 21
21 | Construction | Gym | 15 | 05-09-2025 | 25-09-2025 | 514 | 529 | 13; 15; 20 | 22
22 | Construction | Leisure area | 7 | 26-09-2025 | 06-10-2025 | 529 | 536 | 13; 15; 21 | 23
23 | Construction | Garden | 10 | 07-10-2025 | 20-10-2025 | 536 | 546 | 13; 15; 22 | 24; 27
24 | Construction | Roads | 10 | 21-10-2025 | 03-11-2025 | 546 | 556 | 13; 15; 23 | 25; 26; 27
25 | Construction | Decorative elements | 5 | 04-11-2025 | 10-11-2025 | 556 | 561 | 13; 15; 24 | 27
26 | Construction | Lagoon | 60 | 04-11-2025 | 26-01-2026 | 556 | 616 | 13; 15; 24 | 27
27 | Construction | Urban metallic components installment | 22 | 27-01-2026 | 25-02-2026 | 616 | 638 | 14; 15; 23; 24; 25; 26 | 28
28 | Construction | Soccer field and leisure zone components installment | 15 | 26-02-2026 | 18-03-2026 | 638 | 653 | 14; 15; 27 | 29
29 | Construction | Installation of water dispensers | 15 | 19-03-2026 | 08-04-2026 | 653 | 668 | 14; 15; 28 | 30
30 | Construction | Equipment functionality test | 15 | 09-04-2026 | 29-04-2026 | 668 | 683 | 29 | 31
31 | Construction | Final test supporting document | 10 | 30-04-2026 | 13-05-2026 | 683 | 693 | 30 | 32
32 | Construction | Operations manual | 5 | 14-05-2026 | 20-05-2026 | 693 | 698 | 31 | 33
33 | Post-Contruction | Contracts closure | 3 | 21-05-2026 | 25-05-2026 | 698 | 701 | 32; 4 | 34
34 | Post-Contruction | Project closing report | 1 | 26-05-2026 | 26-05-2026 | 701 | 702 | 33 | 35
35 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 27-05-2026 | 27-05-2026 | 702 | 702 | 34

## P3_Constrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 02-10-2023 | 02-10-2023 | 10 | 10 |  | 3
3 | Pre-Construction | Project planning | 40 | 02-10-2023 | 24-11-2023 | 10 | 50 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 850 | 27-11-2023 | 26-02-2027 | 50 | 900 | 3 | 38
5 | Pre-Construction | Area survey | 15 | 29-01-2024 | 16-02-2024 | 95 | 110 | 3 | 6FC+5; 8
6 | Pre-Construction | Topographic study | 8 | 26-02-2024 | 06-03-2024 | 115 | 123 | 5FC+5 | 7
7 | Pre-Construction | Conceptual design | 8 | 29-04-2024 | 08-05-2024 | 160 | 168 | 6 | 8
8 | Pre-Construction | Architectural design | 15 | 06-06-2024 | 26-06-2024 | 188 | 203 | 7; 5 | 9; 13
9 | Pre-Construction | Bidding | 32 | 03-02-2025 | 18-03-2025 | 360 | 392 | 8 | 14; 26; 22; 10
10 | Pre-Construction | Equipment contracts | 14 | 19-03-2025 | 07-04-2025 | 392 | 406 | 9 | 30; 31; 32; 11
11 | Pre-Construction | Legal permits | 15 | 08-04-2025 | 28-04-2025 | 406 | 421 | 10 | 14; 12
12 | Pre-Construction | Construction license | 15 | 29-04-2025 | 19-05-2025 | 421 | 436 | 11 | 14
13 | Pre-Construction | Operations licenses | 15 | 10-10-2024 | 30-10-2024 | 278 | 293 | 8 | 36
14 | Construction | Existing structure demolition | 10 | 20-05-2025 | 02-06-2025 | 436 | 446 | 11; 12; 9; P1-7; P1-8; P1-9; P2-9 | 15
15 | Construction | Debris removal | 10 | 03-06-2025 | 16-06-2025 | 446 | 456 | 14 | 16
16 | Construction | Earthmoving works | 15 | 17-06-2025 | 07-07-2025 | 456 | 471 | 15 | 17
17 | Construction | Foundations | 15 | 08-07-2025 | 28-07-2025 | 471 | 486 | 16 | 18
18 | Construction | Reinforced concrete structure | 15 | 29-07-2025 | 18-08-2025 | 486 | 501 | 17 | 19
19 | Construction | Vertical walls | 60 | 19-08-2025 | 10-11-2025 | 501 | 561 | 18 | 20
20 | Construction | Thermo-acoustic insulation | 30 | 11-11-2025 | 22-12-2025 | 561 | 591 | 19 | 21
21 | Construction | Walls plaster | 20 | 23-12-2025 | 19-01-2026 | 591 | 611 | 20 | 22
22 | Construction | Sanitary water system | 42 | 20-01-2026 | 18-03-2026 | 611 | 653 | 9; 21 | 23
23 | Construction | Pipeline system | 42 | 19-03-2026 | 15-05-2026 | 653 | 695 | 22 | 24
24 | Construction | Electrical system | 28 | 18-05-2026 | 24-06-2026 | 695 | 723 | 23 | 25; 30
25 | Construction | Mechanical system | 42 | 25-06-2026 | 21-08-2026 | 723 | 765 | 24 | 26; 30
26 | Construction | Floor covering | 30 | 24-08-2026 | 02-10-2026 | 765 | 795 | 9; 25 | 27
27 | Construction | Windows and doors placement | 30 | 05-10-2026 | 13-11-2026 | 795 | 825 | 26 | 28
28 | Construction | Wall patching | 45 | 16-11-2026 | 15-01-2027 | 825 | 870 | 27 | 29
29 | Construction | Painting walls | 50 | 18-01-2027 | 26-03-2027 | 870 | 920 | 28 | 30; 31
30 | Construction | Electrical appliances installment | 60 | 29-03-2027 | 18-06-2027 | 920 | 980 | 10; 29; 25; 24 | 31
31 | Construction | Sanitary facilities installment | 70 | 21-06-2027 | 24-09-2027 | 980 | 1050 | 30; 10; 29 | 32; 33
32 | Construction | Furnitures | 50 | 27-09-2027 | 03-12-2027 | 1050 | 1100 | 31; 10 | 34; 33
33 | Construction | Equipment functionality test | 15 | 06-12-2027 | 24-12-2027 | 1100 | 1115 | 31; 32 | 34
34 | Construction | Equipment installment acceptance | 15 | 27-12-2027 | 14-01-2028 | 1115 | 1130 | 33; 32 | 35
35 | Construction | Building site final cleaning | 10 | 17-01-2028 | 28-01-2028 | 1130 | 1140 | 34 | 36
36 | Construction | Final test supporting document | 10 | 31-01-2028 | 11-02-2028 | 1140 | 1150 | 13; 35 | 37
37 | Construction | Operations manual | 10 | 14-02-2028 | 25-02-2028 | 1150 | 1160 | 36 | 38
38 | Post-Contruction | Contracts closure | 20 | 28-02-2028 | 24-03-2028 | 1160 | 1180 | 37; 4 | 39
39 | Post-Contruction | Project closing report | 30 | 27-03-2028 | 05-05-2028 | 1180 | 1210 | 38 | 40
40 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 08-05-2028 | 08-05-2028 | 1210 | 1210 | 39

## P1_notConstrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 18-09-2023 | 18-09-2023 | 0 | 0 |  | 3
3 | Pre-Construction | Project planning | 30 | 18-09-2023 | 27-10-2023 | 0 | 30 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 150 | 30-10-2023 | 24-05-2024 | 30 | 180 | 3 | 56
5 | Pre-Construction | Conceptual design | 5 | 30-10-2023 | 03-11-2023 | 30 | 35 | 3 | 6
6 | Pre-Construction | Functional requirements definition | 5 | 06-11-2023 | 10-11-2023 | 35 | 40 | 5 | 7; 8; 9
7 | Pre-Construction | Zone 1 design | 8 | 13-11-2023 | 22-11-2023 | 40 | 48 | 6 | 10; 11; 12; 13; 14
8 | Pre-Construction | Zone 2 design | 8 | 13-11-2023 | 22-11-2023 | 40 | 48 | 6 | 10; 11; 12; 13; 29
9 | Pre-Construction | Zone 3 design | 8 | 13-11-2023 | 22-11-2023 | 40 | 48 | 6 | 10; 11; 12; 13
10 | Pre-Construction | Construction tramits | 30 | 23-11-2023 | 03-01-2024 | 48 | 78 | 7; 8; 9 | 14; 29; 54
11 | Pre-Construction | Operations licenses | 25 | 23-11-2023 | 27-12-2023 | 48 | 73 | 7; 8; 9 | 54
12 | Pre-Construction | Insurance contract | 9 | 23-11-2023 | 05-12-2023 | 48 | 57 | 7; 8; 9 | 54
13 | Pre-Construction | Bidding | 15 | 23-11-2023 | 13-12-2023 | 48 | 63 | 7; 8; 9 | 14; 15; 16; 29; 30; 31; 42; 43; 41
14 | Construction | Pipeline system zone 1 | 7 | 06-05-2024 | 14-05-2024 | 165 | 172 | 7; 10; 13; P2-9; P3-8 | 15; 23
15 | Construction | Electrical system zone 1 | 10 | 15-05-2024 | 28-05-2024 | 172 | 182 | 13; 14 | 17; 18; 19; 20; 21; 16
16 | Construction | Air Condition System zone 1 | 5 | 29-05-2024 | 04-06-2024 | 182 | 187 | 13; 15 | 17
17 | Construction | Floor adaptation zone 1 | 3 | 05-06-2024 | 07-06-2024 | 187 | 190 | 15; 16 | 18
18 | Construction | Installation of mirrors | 2 | 10-06-2024 | 11-06-2024 | 190 | 192 | 15; 17 | 19
19 | Construction | Replacement of toilets zone 1 | 5 | 12-06-2024 | 18-06-2024 | 192 | 197 | 15; 18 | 25
20 | Construction | Installation of stair | 7 | 29-05-2024 | 06-06-2024 | 182 | 189 | 15 | 21
21 | Construction | Elevator replacement | 7 | 07-06-2024 | 17-06-2024 | 189 | 196 | 15; 20 | 22
22 | Construction | Installation of turnstiles for employee entry | 2 | 18-06-2024 | 19-06-2024 | 196 | 198 | 21 | 23
23 | Construction | Installation of fiber optics for WiFi zone 1 | 1 | 20-06-2024 | 20-06-2024 | 198 | 199 | 22; 14 | 24
24 | Construction | Installation of water dispensers | 1 | 21-06-2024 | 21-06-2024 | 199 | 200 | 23 | 25
25 | Construction | Wall patching on floor 1 | 8 | 24-06-2024 | 03-07-2024 | 200 | 208 | 24; 19 | 26FC+5
26 | Construction | Painting walls on floor 1 | 5 | 11-07-2024 | 17-07-2024 | 213 | 218 | 25FC+5 | 27; 28
27 | Construction | Adaptation and installation of machinary | 6 | 18-07-2024 | 25-07-2024 | 218 | 224 | 26 | 28
28 | Construction | Furniture installation | 2 | 26-07-2024 | 29-07-2024 | 224 | 226 | 26; 27 | 53
29 | Construction | Pipeline system zone 2 | 6 | 04-01-2024 | 11-01-2024 | 78 | 84 | 8; 10; 13 | 30
30 | Construction | Electrical system zone 2 | 9 | 12-01-2024 | 24-01-2024 | 84 | 93 | 13; 29 | 32; 31; 33
31 | Construction | Air Condition System zone 2 | 5 | 25-01-2024 | 31-01-2024 | 93 | 98 | 13; 30 | 32
32 | Construction | Floor adaptation zone 2 | 3 | 01-02-2024 | 05-02-2024 | 98 | 101 | 30; 31 | 34; 35; 36FC+8
33 | Construction | Installation electrical stair | 14 | 25-01-2024 | 13-02-2024 | 93 | 107 | 30 | 35
34 | Construction | Replacement of toilets zone 2 | 8 | 06-02-2024 | 15-02-2024 | 101 | 109 | 32 | 35
35 | Construction | Elevator door adaptation | 3 | 16-02-2024 | 20-02-2024 | 109 | 112 | 34; 32; 33 | 37
36 | Construction | Installation of fiber optics for WiFi zone 2 | 3 | 16-02-2024 | 20-02-2024 | 109 | 112 | 32FC+8 | 37
37 | Construction | Wall patching on floor zone 2 | 8 | 21-02-2024 | 01-03-2024 | 112 | 120 | 36; 35 | 38FC+5
38 | Construction | Painting walls on floor zone 2 | 5 | 11-03-2024 | 15-03-2024 | 125 | 130 | 37FC+5 | 39; 40
39 | Construction | Nurses room adaptation | 3 | 18-03-2024 | 20-03-2024 | 130 | 133 | 38 | 53
40 | Construction | Medical consultancy rooms | 8 | 18-03-2024 | 27-03-2024 | 130 | 138 | 38 | 41; 53
41 | Construction | Pipeline system zone 3 | 6 | 28-03-2024 | 04-04-2024 | 138 | 144 | 40; 13 | 42; 46; 47
42 | Construction | Electrical system zone 3 | 9 | 05-04-2024 | 17-04-2024 | 144 | 153 | 13; 41 | 43; 45FC+5; 47
43 | Construction | Air Condition System zone 3 | 5 | 18-04-2024 | 24-04-2024 | 153 | 158 | 13; 42 | 44
44 | Construction | Replacement of toilets zone 3 | 3 | 25-04-2024 | 29-04-2024 | 158 | 161 | 43 | 46
45 | Construction | Elevator door adaptation | 2 | 25-04-2024 | 26-04-2024 | 158 | 160 | 42FC+5 | 48
46 | Construction | Installation of fiber optics for WiFi zone 3 | 2 | 30-04-2024 | 01-05-2024 | 161 | 163 | 41; 44 | 48
47 | Construction | Industrial kitchen installment | 10 | 18-04-2024 | 01-05-2024 | 153 | 163 | 41; 42 | 48
48 | Construction | Wall patching on floor zone 3 | 8 | 02-05-2024 | 13-05-2024 | 163 | 171 | 46; 45; 47 | 49FC+5
49 | Construction | Painting walls on floor zone 3 | 5 | 21-05-2024 | 27-05-2024 | 176 | 181 | 48FC+5 | 50; 51; 52FC+2
50 | Construction | Clients room adaptation | 3 | 28-05-2024 | 30-05-2024 | 181 | 184 | 49 | 53
51 | Construction | Dining room adaptation | 3 | 28-05-2024 | 30-05-2024 | 181 | 184 | 49 | 53
52 | Construction | Control Center installment | 1 | 30-05-2024 | 30-05-2024 | 183 | 184 | 49FC+2 | 53
53 | Construction | Equipment functionality test | 3 | 30-07-2024 | 01-08-2024 | 226 | 229 | 28; 40; 52; 39; 50; 51 | 54
54 | Construction | Final test supporting document | 1 | 02-08-2024 | 02-08-2024 | 229 | 230 | 10; 11; 12; 53 | 55
55 | Construction | Operations manual | 1 | 05-08-2024 | 05-08-2024 | 230 | 231 | 54 | 56
56 | Post-Contruction | Contracts closure | 3 | 06-08-2024 | 08-08-2024 | 231 | 234 | 4; 55 | 57
57 | Post-Contruction | Project closing report | 1 | 09-08-2024 | 09-08-2024 | 234 | 235 | 56 | 58
58 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 12-08-2024 | 12-08-2024 | 235 | 235 | 57

## P2_notConstrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 25-09-2023 | 25-09-2023 | 5 | 5 |  | 3
3 | Pre-Construction | Project planning | 60 | 25-09-2023 | 15-12-2023 | 5 | 65 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 500 | 18-12-2023 | 14-11-2025 | 65 | 565 | 3 | 33
5 | Pre-Construction | Documentation analysis | 30 | 18-12-2023 | 26-01-2024 | 65 | 95 | 3 | 6
6 | Pre-Construction | Consultation results report | 30 | 29-01-2024 | 08-03-2024 | 95 | 125 | 5 | 7; 8FC+5
7 | Pre-Construction | Architectural design | 20 | 11-03-2024 | 05-04-2024 | 125 | 145 | 6 | 9
8 | Pre-Construction | Lanscape design | 15 | 18-03-2024 | 05-04-2024 | 130 | 145 | 6FC+5 | 9
9 | Pre-Construction | Final design | 20 | 08-04-2024 | 03-05-2024 | 145 | 165 | 7; 8 | 10; 11; 12; 13FC+20; 14FC+35; 15
10 | Pre-Construction | Legal permits | 30 | 06-05-2024 | 14-06-2024 | 165 | 195 | 9 | 16
11 | Pre-Construction | Environmental permits | 30 | 06-05-2024 | 14-06-2024 | 165 | 195 | 9 | 16
12 | Pre-Construction | Construction license | 30 | 06-05-2024 | 14-06-2024 | 165 | 195 | 9 | 16
13 | Pre-Construction | Providers contracts | 45 | 03-06-2024 | 02-08-2024 | 185 | 230 | 9FC+20 | 17; 18; 19; 20; 21; 22; 23; 24; 25; 26
14 | Pre-Construction | Components contracts | 30 | 24-06-2024 | 02-08-2024 | 200 | 230 | 9FC+35 | 27; 28; 29
15 | Pre-Construction | Procurement documents | 70 | 06-05-2024 | 09-08-2024 | 165 | 235 | 9 | 16; 17; 18; 19; 20; 21; 22; 23; 24; 25; 26; 27; 28; 29
16 | Construction | Site preparation | 25 | 12-08-2024 | 13-09-2024 | 235 | 260 | 10; 11; 12; 15; P1-7; P1-8; P1-9; P3-8 | 17
17 | Construction | Sanitary Water system | 18 | 16-09-2024 | 09-10-2024 | 260 | 278 | 13; 15; 16 | 18
18 | Construction | Electrical system | 43 | 10-10-2024 | 09-12-2024 | 278 | 321 | 13; 15; 17 | 19; 20
19 | Construction | Soccer field | 36 | 10-12-2024 | 28-01-2025 | 321 | 357 | 13; 15; 18 | 20
20 | Construction | Changing rooms & toilettes | 39 | 29-01-2025 | 24-03-2025 | 357 | 396 | 13; 15; 18; 19 | 21
21 | Construction | Gym | 15 | 25-03-2025 | 14-04-2025 | 396 | 411 | 13; 15; 20 | 22
22 | Construction | Leisure area | 7 | 15-04-2025 | 23-04-2025 | 411 | 418 | 13; 15; 21 | 23
23 | Construction | Garden | 10 | 24-04-2025 | 07-05-2025 | 418 | 428 | 13; 15; 22 | 24; 27
24 | Construction | Roads | 10 | 08-05-2025 | 21-05-2025 | 428 | 438 | 13; 15; 23 | 25; 26; 27
25 | Construction | Decorative elements | 5 | 22-05-2025 | 28-05-2025 | 438 | 443 | 13; 15; 24 | 27
26 | Construction | Lagoon | 60 | 22-05-2025 | 13-08-2025 | 438 | 498 | 13; 15; 24 | 27
27 | Construction | Urban metallic components installment | 22 | 14-08-2025 | 12-09-2025 | 498 | 520 | 14; 15; 23; 24; 25; 26 | 28
28 | Construction | Soccer field and leisure zone components installment | 15 | 15-09-2025 | 03-10-2025 | 520 | 535 | 14; 15; 27 | 29
29 | Construction | Installation of water dispensers | 15 | 06-10-2025 | 24-10-2025 | 535 | 550 | 14; 15; 28 | 30
30 | Construction | Equipment functionality test | 15 | 27-10-2025 | 14-11-2025 | 550 | 565 | 29 | 31
31 | Construction | Final test supporting document | 10 | 17-11-2025 | 28-11-2025 | 565 | 575 | 30 | 32
32 | Construction | Operations manual | 5 | 01-12-2025 | 05-12-2025 | 575 | 580 | 31 | 33
33 | Post-Contruction | Contracts closure | 3 | 08-12-2025 | 10-12-2025 | 580 | 583 | 32; 4 | 34
34 | Post-Contruction | Project closing report | 1 | 11-12-2025 | 11-12-2025 | 583 | 584 | 33 | 35
35 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 12-12-2025 | 12-12-2025 | 584 | 584 | 34

## P3_notConstrained
Task Label | Section | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
2 | Pre-Construction | Contract signing | 0 | 02-10-2023 | 02-10-2023 | 10 | 10 |  | 3
3 | Pre-Construction | Project planning | 40 | 02-10-2023 | 24-11-2023 | 10 | 50 | 2 | 4; 5
4 | Pre-Construction | Project execution and controlling | 850 | 27-11-2023 | 26-02-2027 | 50 | 900 | 3 | 38
5 | Pre-Construction | Area survey | 15 | 27-11-2023 | 15-12-2023 | 50 | 65 | 3 | 6FC+5; 8
6 | Pre-Construction | Topographic study | 8 | 25-12-2023 | 03-01-2024 | 70 | 78 | 5FC+5 | 7
7 | Pre-Construction | Conceptual design | 8 | 04-01-2024 | 15-01-2024 | 78 | 86 | 6 | 8
8 | Pre-Construction | Architectural design | 15 | 16-01-2024 | 05-02-2024 | 86 | 101 | 7; 5 | 9; 13
9 | Pre-Construction | Bidding | 32 | 06-02-2024 | 20-03-2024 | 101 | 133 | 8 | 14; 26; 22; 10
10 | Pre-Construction | Equipment contracts | 14 | 21-03-2024 | 09-04-2024 | 133 | 147 | 9 | 30; 31; 32; 11
11 | Pre-Construction | Legal permits | 15 | 10-04-2024 | 30-04-2024 | 147 | 162 | 10 | 14; 12
12 | Pre-Construction | Construction license | 15 | 01-05-2024 | 21-05-2024 | 162 | 177 | 11 | 14
13 | Pre-Construction | Operations licenses | 15 | 06-02-2024 | 26-02-2024 | 101 | 116 | 8 | 36
14 | Construction | Existing structure demolition | 10 | 22-05-2024 | 04-06-2024 | 177 | 187 | 11; 12; 9; P1-7; P1-8; P1-9; P2-9 | 15
15 | Construction | Debris removal | 10 | 05-06-2024 | 18-06-2024 | 187 | 197 | 14 | 16
16 | Construction | Earthmoving works | 15 | 19-06-2024 | 09-07-2024 | 197 | 212 | 15 | 17
17 | Construction | Foundations | 15 | 10-07-2024 | 30-07-2024 | 212 | 227 | 16 | 18
18 | Construction | Reinforced concrete structure | 15 | 31-07-2024 | 20-08-2024 | 227 | 242 | 17 | 19
19 | Construction | Vertical walls | 60 | 21-08-2024 | 12-11-2024 | 242 | 302 | 18 | 20
20 | Construction | Thermo-acoustic insulation | 30 | 13-11-2024 | 24-12-2024 | 302 | 332 | 19 | 21
21 | Construction | Walls plaster | 20 | 25-12-2024 | 21-01-2025 | 332 | 352 | 20 | 22
22 | Construction | Sanitary water system | 42 | 22-01-2025 | 20-03-2025 | 352 | 394 | 9; 21 | 23
23 | Construction | Pipeline system | 42 | 21-03-2025 | 19-05-2025 | 394 | 436 | 22 | 24
24 | Construction | Electrical system | 28 | 20-05-2025 | 26-06-2025 | 436 | 464 | 23 | 25; 30
25 | Construction | Mechanical system | 42 | 27-06-2025 | 25-08-2025 | 464 | 506 | 24 | 26; 30
26 | Construction | Floor covering | 30 | 26-08-2025 | 06-10-2025 | 506 | 536 | 9; 25 | 27
27 | Construction | Windows and doors placement | 30 | 07-10-2025 | 17-11-2025 | 536 | 566 | 26 | 28
28 | Construction | Wall patching | 45 | 18-11-2025 | 19-01-2026 | 566 | 611 | 27 | 29
29 | Construction | Painting walls | 50 | 20-01-2026 | 30-03-2026 | 611 | 661 | 28 | 30; 31
30 | Construction | Electrical appliances installment | 60 | 31-03-2026 | 22-06-2026 | 661 | 721 | 10; 29; 25; 24 | 31
31 | Construction | Sanitary facilities installment | 70 | 23-06-2026 | 28-09-2026 | 721 | 791 | 30; 10; 29 | 32; 33
32 | Construction | Furnitures | 50 | 29-09-2026 | 07-12-2026 | 791 | 841 | 31; 10 | 34; 33
33 | Construction | Equipment functionality test | 15 | 08-12-2026 | 28-12-2026 | 841 | 856 | 31; 32 | 34
34 | Construction | Equipment installment acceptance | 15 | 29-12-2026 | 18-01-2027 | 856 | 871 | 33; 32 | 35
35 | Construction | Building site final cleaning | 10 | 19-01-2027 | 01-02-2027 | 871 | 881 | 34 | 36
36 | Construction | Final test supporting document | 10 | 02-02-2027 | 15-02-2027 | 881 | 891 | 13; 35 | 37
37 | Construction | Operations manual | 10 | 16-02-2027 | 01-03-2027 | 891 | 901 | 36 | 38
38 | Post-Contruction | Contracts closure | 20 | 02-03-2027 | 29-03-2027 | 901 | 921 | 37; 4 | 39
39 | Post-Contruction | Project closing report | 30 | 30-03-2027 | 10-05-2027 | 921 | 951 | 38 | 40
40 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 11-05-2027 | 11-05-2027 | 951 | 951 | 39