## P1_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 0 | 0 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 0 | 80 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 80 | 160 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 160 | 240 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 240 | 240 | 3, 4, 5

## P1_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 0 | 0 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 0 | 80 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 0 | 80 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 0 | 80 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 80 | 80 | 3, 4, 5

## P2_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 10 | 10 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 10 | 90 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 90 | 170 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 170 | 250 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 250 | 250 | 3, 4, 5

## P2_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 10 | 10 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 10 | 90 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 10 | 90 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 10 | 90 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 90 | 90 | 3, 4, 5

## P3_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 20 | 20 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 20 | 100 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 100 | 180 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 180 | 260 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 260 | 260 | 3, 4, 5

## P3_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 20 | 20 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 20 | 100 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 20 | 100 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 20 | 100 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 100 | 100 | 3, 4, 5