## Tasks
ID | Section | Name | Duration | Predecessors | Successors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12 | R13 | R14 | R15 | R16 | R17 | R18 | R19 | R20 | R21 | R22 | R23 | R24 | R25
2 |  | Contract signing | 0 |  | 3 | bar: R18
3 |  | Project planning | 30 | 2 | 4;5 | bar: R18
4 |  | Project execution and controlling | 159 | 3 | 56
5 |  | Conceptual design | 5 | 3 | 6 | R14: 2; R15: 2
6 |  | Functional requirements definition | 5 | 5 | 7;8;9 | bar: R14 to R15
7 |  | Zone 1 design | 8 | 6 | 10;11;12;13;14 | R14: 2; R15: 3
8 |  | Zone 2 design | 8 | 6 | 10;11;12;13;29 | R14: 2; R15: 3
9 |  | Zone 3 design | 8 | 6 | 10;11;12;13 | R14: 2; R15: 3
10 |  | Construction tramits | 30 | 7;8;9 | 14;29;54 | bar: R23
11 |  | Operations licenses | 25 | 7;8;9 | 54 | bar: R23
12 |  | Insurance contract | 9 | 7;8;9 | 54 | bar: R23
13 |  | Bidding | 15 | 7;8;9 | 14;15;16;29;30;31;42;43;41 | bar: R24
14 |  | Pipeline system zone 1 | 7 | 7;10;13 | 15;23 | bar: R3; R25
15 |  | Electrical system zone 1 | 10 | 13;14 | 17;18;19;20;21;16 | bar: R1
16 |  | Air Condition System zone 1 | 5 | 13;15 | 17 | bar: R4
17 |  | Floor adaptation zone 1 | 3 | 15;16 | 18 | bar: R5
18 |  | Installation of mirrors | 2 | 15;17 | 19 | bar: R9
19 |  | Replacement of toilets zone 1 | 5 | 15;18 | 25 | bar: R2
20 |  | Installation of stair | 7 | 15 | 21 | bar: R8
21 |  | Elevator replacement | 7 | 15;20 | 22 | bar: R8
22 |  | Installation of turnstiles for employee entry | 2 | 21 | 23 | bar: R9
23 |  | Installation of fiber optics for WiFi zone 1 | 1 | 22;14 | 24 | bar: R7
24 |  | Installation of water dispensers | 1 | 23 | 25 | bar: R2
25 |  | Wall patching on floor 1 | 8 | 24;19 | 26FC+5 | bar: R6
26 |  | Painting walls on floor 1 | 5 | 25FC+5 | 27;28 | bar: R6
27 |  | Adaptation and installation of machinary | 6 | 26 | 28 | bar: R1
28 |  | Furniture installation | 2 | 26;27 | 53 | bar: R9
29 |  | Pipeline system zone 2 | 6 | 8;10;13 | 30 | bar: R3
30 |  | Electrical system zone 2 | 9 | 13;29 | 32;31;33 | bar: R1
31 |  | Air Condition System zone 2 | 5 | 13;30 | 32 | bar: R4
32 |  | Floor adaptation zone 2 | 3 | 30;31 | 34;35;36FC+8 | bar: R5
33 |  | Installation electrical stair | 14 | 30 | 35 | bar: R8
34 |  | Replacement of toilets zone 2 | 8 | 32 | 35 | bar: R2
35 |  | Elevator door adaptation | 3 | 34;32;33 | 37 | bar: R8
36 |  | Installation of fiber optics for WiFi zone 2 | 3 | 32FC+8 | 37 | bar: R7
37 |  | Wall patching on floor zone 2 | 8 | 36;35 | 38FC+5 | bar: R6
38 |  | Painting walls on floor zone 2 | 5 | 37FC+5 | 39;40 | bar: R6
39 |  | Nurses room adaptation | 3 | 38 | 53 | bar: R9
40 |  | Medical consultancy rooms | 8 | 38 | 41;53 | bar: R9
41 |  | Pipeline system zone 3 | 6 | 40;13 | 42;46;47 | bar: R3
42 |  | Electrical system zone 3 | 9 | 13;41 | 43;45FC+5;47 | bar: R1
43 |  | Air Condition System zone 3 | 5 | 13;42 | 44 | bar: R4
44 |  | Replacement of toilets zone 3 | 3 | 43 | 46 | bar: R2
45 |  | Elevator door adaptation | 2 | 42FC+5 | 48 | bar: R8
46 |  | Installation of fiber optics for WiFi zone 3 | 2 | 41;44 | 48 | bar: R7
47 |  | Industrial kitchen installment | 10 | 41;42 | 48 | bar: R9
48 |  | Wall patching on floor zone 3 | 8 | 46;45;47 | 49FC+5 | bar: R6
49 |  | Painting walls on floor zone 3 | 5 | 48FC+5 | 50;51;52FC+2 | bar: R6
50 |  | Clients room adaptation | 3 | 49 | 53 | bar: R9
51 |  | Dining room adaptation | 3 | 49 | 53 | bar: R9
52 |  | Control Center installment | 1 | 49FC+2 | 53 | bar: R9
53 |  | Equipment functionality test | 3 | 28;40;52;39;50;51 | 54 | bar: R12; R14; R16; R21 to R22
54 |  | Final test supporting document | 1 | 10;11;12;53 | 55 | bar: R17; R21 to R22
55 |  | Operations manual | 1 | 54 | 56 | bar: R21 to R22
56 |  | Contracts closure | 3 | 4;55 | 57 | bar: R18; R23 to R25
57 |  | Project closing report | 1 | 56 | 58 | bar: R18
58 |  | ACCEPTANCE Project 1 | 0 | 57

## Resources
ID | Name | Type | Units
R1 | Electrical system | HC | 1
R2 | Sanitary water system | HC | 1
R3 | Pipeline system | HC | 1
R4 | Air Condition system | HC | 1
R5 | Floor and vertical walls | HC | 1
R6 | Wall patching & painting | HC | 1
R7 | WIFI fiber optic | HC | 1
R8 | Electrical stair and elevator | HC | 1
R9 | Medical Center components and furniture | HC | 1
R10 | Urban renewal components and furniture | HC | 1
R11 | Hotel components and furniture | HC | 1
R12 | Testings | HC | 1
R13 | Demolition and removal | HC | 1
R14 | Architect Sr | HC | 3
R15 | Architect Jr | HC | 5
R16 | Engineer Sr | HC | 2
R17 | Engineer Jr | HC | 4
R18 | PM 1 | HC | 1
R19 | PM 2 | HC | 1
R20 | PM 3 | HC | 1
R21 | Quality Manager Sr | HC | 2
R22 | Quality Manager Jr | HC | 1
R23 | Lawyer and Legal Specialist | HC | 2
R24 | Procurement Manager | HC | 1
R25 | Procurement Assistant | HC | 2