## Tasks
ID | Section | Name | Duration | Predecessors | Successors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12 | R13 | R14 | R15 | R16 | R17 | R18 | R19 | R20 | R21 | R22 | R23 | R24 | R25
3 |  | Contract signing | 0 |  | 5
5 |  | Project planning | 60 | 3 | 6;8 | bar: R19
6 |  | Project execution and controlling | 516 | 5 | 44 | bar: R19
8 |  | Documentation analysis | 30 | 5 | 9 | R14: 2; R15: 2
9 |  | Consultation results report | 30 | 8 | 11;12FC+5 | bar: R14 to R17
11 |  | Architectural design | 20 | 9 | 13 | R14: 1; R16: 2
12 |  | Lanscape design | 15 | 9FC+5 | 13 | R14: 1; R15: 2
13 |  | Final design | 20 | 11;12 | 15;16;17;19FC+20;20FC+35;21 | R14: 1; R15: 3; R16: 2; R17: 2
15 |  | Legal permits | 30 | 13 | 23 | R23: 2
16 |  | Environmental permits | 30 | 13 | 23 | bar: R23
17 |  | Construction license | 30 | 13 | 23 | R23: 2
19 |  | Providers contracts | 45 | 13FC+20 | 24;25;27;28;30;31;33;34;35;36 | R24: 1; R25: 2
20 |  | Components contracts | 30 | 13FC+35 | 38;39;40 | R24: 1; R25: 2
21 |  | Procurement documents | 70 | 13 | 23;24;25;27;28;30;31;33;34;35;36;38;39;40 | R24: 1; R25: 2
23 |  | Site preparation | 25 | 15;16;17;21 | 24 | bar: R13
24 |  | Sanitary Water system | 18 | 19;21;23 | 25 | bar: R2
25 |  | Electrical system | 43 | 19;21;24 | 27;28 | bar: R1
27 |  | Soccer field | 36 | 19;21;25 | 28 | bar: R3; R10
28 |  | Changing rooms & toilettes | 39 | 19;21;25;27 | 30 | bar: R10
30 |  | Gym | 15 | 19;21;28 | 31 | bar: R10
31 |  | Leisure area | 7 | 19;21;30 | 33 | bar: R10
33 |  | Garden | 10 | 19;21;31 | 34;38
34 |  | Roads | 10 | 19;21;33 | 35;36;38 | bar: R10
35 |  | Decorative elements | 5 | 19;21;34 | 38 | bar: R10
36 |  | Lagoon | 60 | 19;21;34 | 38 | bar: R10
38 |  | Urban metallic components installment | 22 | 20;21;33;34;35;36 | 39
39 |  | Soccer field and leisure zone components installment | 15 | 20;21;38 | 40 | bar: R10
40 |  | Installation of water dispensers | 15 | 20;21;39 | 42 | bar: R10
42 |  | Equipment functionality test | 15 | 40 | 43 | R12: 1; R14: 1; R15: 1; R16: 1; R17: 1; R21: 2; R22: 1
43 |  | Final test supporting document | 10 | 42 | 44 | R16: 2; R17: 3; R21: 1; R22: 1
44 |  | Operations manual | 5 | 43;6 | 46 | bar: R16 to R17; R21 to R22
46 |  | Contracts closure | 3 | 44 | 47 | bar: R19; R23 to R25
47 |  | Project closing report | 1 | 46 | 48 | bar: R19
48 |  | ACCEPTANCE Project 1 | 0 | 47

## Resources
ID | Name | Type | Units
R1 | Eletrical system | HC | 1
R2 | Sanitary water system | HC | 1
R3 | Pipeline system | HC | 1
R4 | Air Condition system | HC | 1
R5 | Floor and vertical walls | HC | 1
R6 | Wall patching & painting | HC | 1
R7 | WIFI fiber optic | HC | 1
R8 | Electrical stair and elevator | HC | 1
R9 | Medical Center components and furniture | HC | 1
R10 | Urban renewal components and furniture | HC | 1
R11 | Hotel components and furniture | HC | 1
R12 | Testings | HC | 1
R13 | Demolition and removal | HC | 1
R14 | Architect Sr | HC | 3
R15 | Architect Jr | HC | 5
R16 | Engineer Sr | HC | 2
R17 | Engineer Jr | HC | 4
R18 | PM 1 | HC | 1
R19 | PM 2 | HC | 1
R20 | PM 3 | HC | 1
R21 | Quality Manager Sr | HC | 2
R22 | Quality Manager Jr | HC | 1
R23 | Lawyer and Legal Specialist | HC | 2
R24 | Procurement Manager | HC | 1
R25 | Procurement Assistant | HC | 2