## Tasks
ID | Section | Name | Duration | Predecessors | Successors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12 | R13 | R14 | R15 | R16 | R17 | R18 | R19 | R20 | R21 | R22 | R23 | R24 | R25
3 |  | Contract signing | 0 |  | 5
5 |  | Project planning | 40 | 3 | 6;8 | bar: R20
6 |  | Project execution and controlling | 600 | 5 | 46 | bar: R20
8 |  | Area survey | 15 | 5 | 9FC+5;11 | R14: 3; R15: 2; R16: 2; R17: 3
9 |  | Topographic study | 8 | 8FC+5 | 10 | R14: 2; R15: 3
10 |  | Conceptual design | 8 | 9 | 11 | R14: 3; R15: 5; R16: 2; R17: 4
11 |  | Architectural design | 15 | 10;8 | 13;18 | R14: 3; R15: 5; R16: 2; R17: 4
13 |  | Bidding | 32 | 11 | 20;34;29;14 | R14: 1; R15: 1; R16: 1; R17: 1; R24: 1; R25: 2
14 |  | Equipment contracts | 14 | 13 | 38;39;40;16 | R14: 1; R15: 1; R16: 1; R17: 1; R24: 1; R25: 2
16 |  | Legal permits | 15 | 14 | 20;17 | R23: 2
17 |  | Construction license | 15 | 16 | 20 | R14: 1; R16: 1; R23: 2
18 |  | Operations licenses | 15 | 11 | 45 | R14: 1; R16: 1; R23: 2
20 |  | Existing structure demolition | 10 | 16;17;13 | 21 | bar: R13
21 |  | Debris removal | 10 | 20 | 22 | bar: R13
22 |  | Earthmoving works | 15 | 21 | 23 | bar: R13
23 |  | Foundations | 15 | 22 | 24 | bar: R13
24 |  | Reinforced concrete structure | 15 | 23 | 25 | bar: R13
25 |  | Vertical walls | 60 | 24 | 26 | bar: R5
26 |  | Thermo-acoustic insulation | 30 | 25 | 27 | bar: R5
27 |  | Walls plaster | 20 | 26 | 29 | bar: R5
29 |  | Sanitary water system | 42 | 13;27 | 30 | bar: R2
30 |  | Pipeline system | 42 | 29 | 31 | bar: R3
31 |  | Electrical system | 28 | 30 | 32;38 | bar: R1
32 |  | Mechanical system | 42 | 31 | 34;38 | bar: R1
34 |  | Floor covering | 30 | 13;32 | 35 | bar: R5
35 |  | Windows and doors placement | 30 | 34 | 36 | bar: R6
36 |  | Wall patching | 45 | 35 | 37 | bar: R6
37 |  | Painting walls | 50 | 36 | 38;39 | bar: R6
38 |  | Electrical appliances installment | 60 | 14;37;32;31 | 39 | bar: R11
39 |  | Sanitary facilities installment | 70 | 38;14;37 | 40;42 | bar: R11
40 |  | Furnitures | 50 | 39;14 | 43;42 | bar: R11
42 |  | Equipment functionality test | 15 | 39;40 | 43 | R12: 1; R14: 1; R16: 1; R21: 2; R22: 1
43 |  | Equipment installment acceptance | 15 | 42;40 | 44 | R14: 2; R16: 2; R21: 2; R22: 1
44 |  | Building site final cleaning | 10 | 43 | 45 | bar: R21 to R22
45 |  | Final test supporting document | 10 | 18;44 | 46 | R17: 2; R21: 2; R22: 1
46 |  | Operations manual | 10 | 45;6 | 48 | R16: 2; R17: 1; R21: 2; R22: 1
48 |  | Contracts closure | 20 | 46 | 49 | R16: 1; R17: 2; R20: 1; R23: 2; R24: 1; R25: 2
49 |  | Project closing report | 30 | 48 | 50 | bar: R20
50 |  | ACCEPTANCE Project 1 | 0 | 49

## Resources
ID | Name | Type | Units
R1 | Eletrical system | HC | 1
R2 | Sanitary water system | HC | 1
R3 | Pipeline system | HC | 1
R4 | Air Condition system | HC | 1
R5 | Floor and vertical walls | HC | 1
R6 | Wall patching & painting | HC | 1
R7 | WIFI fiber optic | HC | 1
R8 | Electrical stair and elevator | HC | 1
R9 | Medical Center components and furniture | HC | 1
R10 | Urban renewal components and furniture | HC | 1
R11 | Hotel components and furniture | HC | 1
R12 | Testings | HC | 1
R13 | Demolition and removal | HC | 1
R14 | Architect Sr | HC | 3
R15 | Architect Jr | HC | 5
R16 | Engineer Sr | HC | 2
R17 | Engineer Jr | HC | 4
R18 | PM 1 | HC | 1
R19 | PM 2 | HC | 1
R20 | PM 3 | HC | 1
R21 | Quality Manager Sr | HC | 2
R22 | Quality Manager Jr | HC | 1
R23 | Lawyer and Legal Specialist | HC | 2
R24 | Procurement Manager | HC | 1
R25 | Procurement Assistant | HC | 2