## Solution
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 40 | 0 | 40 | 3 | 6, 8
6 | Project execution and controlling | 600 | 40 | 640 | 5 | 46
8 | Area survey | 15 | 40 | 55 | 5 | 9FC+5, 11
9 | Topographic study | 8 | 60 | 68 | 8FC+5 | 10
10 | Conceptual design | 8 | 68 | 76 | 9 | 11
11 | Architectural design | 15 | 76 | 91 | 10, 8 | 13, 18
13 | Bidding | 32 | 91 | 123 | 11 | 20, 34, 29, 14
18 | Operations licenses | 15 | 91 | 106 | 11 | 45
14 | Equipment contracts | 14 | 123 | 137 | 13 | 38, 39, 40, 16
16 | Legal permits | 15 | 137 | 152 | 14 | 20, 17
17 | Construction license | 15 | 152 | 167 | 16 | 20
20 | Existing structure demolition | 10 | 167 | 177 | 16, 17, 13 | 21
21 | Debris removal | 10 | 177 | 187 | 20 | 22
22 | Earthmoving works | 15 | 187 | 202 | 21 | 23
23 | Foundations | 15 | 202 | 217 | 22 | 24
24 | Reinforced concrete structure | 15 | 217 | 232 | 23 | 25
25 | Vertical walls | 60 | 232 | 292 | 24 | 26
26 | Thermo-acoustic insulation | 30 | 292 | 322 | 25 | 27
27 | Walls plaster | 20 | 322 | 342 | 26 | 29
29 | Sanitary water system | 42 | 342 | 384 | 13, 27 | 30
30 | Pipeline system | 42 | 384 | 426 | 29 | 31
31 | Electrical system | 28 | 426 | 454 | 30 | 32, 38
32 | Mechanical system | 42 | 454 | 496 | 31 | 34, 38
34 | Floor covering | 30 | 496 | 526 | 13, 32 | 35
35 | Windows and doors placement | 30 | 526 | 556 | 34 | 36
36 | Wall patching | 45 | 556 | 601 | 35 | 37
37 | Painting walls | 50 | 601 | 651 | 36 | 38, 39
38 | Electrical appliances installment | 60 | 651 | 711 | 14, 37, 32, 31 | 39
39 | Sanitary facilities installment | 70 | 711 | 781 | 38, 14, 37 | 40, 42
40 | Furnitures | 50 | 781 | 831 | 39, 14 | 43, 42
42 | Equipment functionality test | 15 | 831 | 846 | 39, 40 | 43
43 | Equipment installment acceptance | 15 | 846 | 861 | 42, 40 | 44
44 | Building site final cleaning | 10 | 861 | 871 | 43 | 45
45 | Final test supporting document | 10 | 871 | 881 | 18, 44 | 46
46 | Operations manual | 10 | 881 | 891 | 45, 6 | 48
48 | Contracts closure | 20 | 891 | 911 | 46 | 49
49 | Project closing report | 30 | 911 | 941 | 48 | 50
50 | ACCEPTANCE Project 1 | 0 | 941 | 941 | 49

## Additional Info
Time
941