## P1_Constrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 18-09-2023 | 18-09-2023 | 0 | 0 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 18-09-2023 | 05-01-2024 | 0 | 80 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 08-01-2024 | 26-04-2024 | 80 | 160 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 29-04-2024 | 16-08-2024 | 160 | 240 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 19-08-2024 | 19-08-2024 | 240 | 240 | 2, 3, 4

## P2_Constrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 25-09-2023 | 25-09-2023 | 5 | 5 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 19-08-2024 | 06-12-2024 | 240 | 320 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 09-12-2024 | 28-03-2025 | 320 | 400 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 31-03-2025 | 18-07-2025 | 400 | 480 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 21-07-2025 | 21-07-2025 | 480 | 480 | 2, 3, 4

## P3_Constrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 02-10-2023 | 02-10-2023 | 10 | 10 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 21-07-2025 | 07-11-2025 | 480 | 560 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 10-11-2025 | 27-02-2026 | 560 | 640 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 02-03-2026 | 19-06-2026 | 640 | 720 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 22-06-2026 | 22-06-2026 | 720 | 720 | 2, 3, 4

## P1_notConstrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 18-09-2023 | 18-09-2023 | 0 | 0 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 18-09-2023 | 05-01-2024 | 0 | 80 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 18-09-2023 | 05-01-2024 | 0 | 80 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 18-09-2023 | 05-01-2024 | 0 | 80 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 08-01-2024 | 08-01-2024 | 80 | 80 | 2, 3, 4

## P2_notConstrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 25-09-2023 | 25-09-2023 | 5 | 5 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 25-09-2023 | 12-01-2024 | 5 | 85 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 25-09-2023 | 12-01-2024 | 5 | 85 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 25-09-2023 | 12-01-2024 | 5 | 85 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 15-01-2024 | 15-01-2024 | 85 | 85 | 2, 3, 4

## P3_notConstrained
Task Label | Task Name | Duration | Start Date | Finish Date | Start Time | Finish Time | Predecessors | Successors
1 | Contract signing | 0 | 02-10-2023 | 02-10-2023 | 10 | 10 |  | 2, 3, 4
2 | Layout definition(VDR) | 80 | 02-10-2023 | 19-01-2024 | 10 | 90 | 1 | 5
3 | STRUCTURAL DESIGN | 80 | 02-10-2023 | 19-01-2024 | 10 | 90 | 1 | 5
4 | EQUIPMENT DESIGN | 80 | 02-10-2023 | 19-01-2024 | 10 | 90 | 1 | 5
5 | FINAL DESIGN REVIEW | 0 | 22-01-2024 | 22-01-2024 | 90 | 90 | 2, 3, 4