## P1
ID | Section | Name | Duration | Predecessors | Successors | Pred other projects | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
2 |  | Contract signing | 0 |  | 3 | bar: R5
3 |  | Project planning | 30 | 2 | 4;5 | bar: R5
4 |  | Project execution and controlling | 159 | 3 | 56
5 |  | Conceptual design | 5 | 3 | 6 |  | R1: 2; R2: 2
6 |  | Functional requirements definition | 5 | 5 | 7;8;9 | bar: R1 to R2
7 |  | Zone 1 design | 8 | 6 | 10;11;12;13;14 |  | R1: 2; R2: 3
8 |  | Zone 2 design | 8 | 6 | 10;11;12;13;29 |  | R1: 2; R2: 3
9 |  | Zone 3 design | 8 | 6 | 10;11;12;13 |  | R1: 2; R2: 3
10 |  | Construction tramits | 30 | 7;8;9 | 14;29;54 | bar: R10
11 |  | Operations licenses | 25 | 7;8;9 | 54 | bar: R10
12 |  | Insurance contract | 9 | 7;8;9 | 54 | bar: R10
13 |  | Bidding | 15 | 7;8;9 | 14;15;16;29;30;31;42;43;41 | bar: R11
14 |  | Pipeline system zone 1 | 7 | 7;10;13 | 15;23 | bar: R12
15 |  | Electrical system zone 1 | 10 | 13;14 | 17;18;19;20;21;16
16 |  | Air Condition System zone 1 | 5 | 13;15 | 17
17 |  | Floor adaptation zone 1 | 3 | 15;16 | 18
18 |  | Installation of mirrors | 2 | 15;17 | 19
19 |  | Replacement of toilets zone 1 | 5 | 15;18 | 25
20 |  | Installation of stair | 7 | 15 | 21
21 |  | Elevator replacement | 7 | 15;20 | 22
22 |  | Installation of turnstiles for employee entry | 2 | 21 | 23
23 |  | Installation of fiber optics for WiFi zone 1 | 1 | 22;14 | 24
24 |  | Installation of water dispensers | 1 | 23 | 25
25 |  | Wall patching on floor 1 | 8 | 24;19 | 26FC+5
26 |  | Painting walls on floor 1 | 5 | 25FC+5 | 27;28
27 |  | Adaptation and installation of machinary | 6 | 26 | 28
28 |  | Furniture installation | 2 | 26;27 | 53
29 |  | Pipeline system zone 2 | 6 | 8;10;13 | 30
30 |  | Electrical system zone 2 | 9 | 13;29 | 32;31;33
31 |  | Air Condition System zone 2 | 5 | 13;30 | 32
32 |  | Floor adaptation zone 2 | 3 | 30;31 | 34;35;36FC+8
33 |  | Installation electrical stair | 14 | 30 | 35
34 |  | Replacement of toilets zone 2 | 8 | 32 | 35
35 |  | Elevator door adaptation | 3 | 34;32;33 | 37
36 |  | Installation of fiber optics for WiFi zone 2 | 3 | 32FC+8 | 37
37 |  | Wall patching on floor zone 2 | 8 | 36;35 | 38FC+5
38 |  | Painting walls on floor zone 2 | 5 | 37FC+5 | 39;40
39 |  | Nurses room adaptation | 3 | 38 | 53
40 |  | Medical consultancy rooms | 8 | 38 | 41;53
41 |  | Pipeline system zone 3 | 6 | 40;13 | 42;46;47
42 |  | Electrical system zone 3 | 9 | 13;41 | 43;45FC+5;47
43 |  | Air Condition System zone 3 | 5 | 13;42 | 44
44 |  | Replacement of toilets zone 3 | 3 | 43 | 46
45 |  | Elevator door adaptation | 2 | 42FC+5 | 48
46 |  | Installation of fiber optics for WiFi zone 3 | 2 | 41;44 | 48
47 |  | Industrial kitchen installment | 10 | 41;42 | 48
48 |  | Wall patching on floor zone 3 | 8 | 46;45;47 | 49FC+5
49 |  | Painting walls on floor zone 3 | 5 | 48FC+5 | 50;51;52FC+2
50 |  | Clients room adaptation | 3 | 49 | 53
51 |  | Dining room adaptation | 3 | 49 | 53
52 |  | Control Center installment | 1 | 49FC+2 | 53
53 |  | Equipment functionality test | 3 | 28;40;52;39;50;51 | 54 | bar: R1; R3; R8 to R9
54 |  | Final test supporting document | 1 | 10;11;12;53 | 55 | bar: R4; R8 to R9
55 |  | Operations manual | 1 | 54 | 56 | bar: R8 to R9
56 |  | Contracts closure | 3 | 4;55 | 57 | bar: R5; R10 to R12
57 |  | Project closing report | 1 | 56 | 58 | bar: R5
58 |  | ACCEPTANCE Project 1 | 0 | 57

## P2
ID | Section | Name | Duration | Predecessors | Successors | Pred other projects | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
3 |  | Contract signing | 0 |  | 5
5 |  | Project planning | 60 | 3 | 6;8 | bar: R6
6 |  | Project execution and controlling | 516 | 5 | 44 | bar: R6
8 |  | Documentation analysis | 30 | 5 | 9 |  | R1: 2; R2: 2
9 |  | Consultation results report | 30 | 8 | 11;12FC+5 | bar: R1 to R4
11 |  | Architectural design | 20 | 9 | 13 |  | R1: 1; R3: 2
12 |  | Lanscape design | 15 | 9FC+5 | 13 |  | R1: 1; R2: 2
13 |  | Final design | 20 | 11;12 | 15;16;17;19FC+20;20FC+35;21 |  | R1: 1; R2: 3; R3: 2; R4: 2
15 |  | Legal permits | 30 | 13 | 23 |  | R10: 2
16 |  | Environmental permits | 30 | 13 | 23 | bar: R10
17 |  | Construction license | 30 | 13 | 23 |  | R10: 2
19 |  | Providers contracts | 45 | 13FC+20 | 24;25;27;28;30;31;33;34;35;36 |  | R11: 1; R12: 2
20 |  | Components contracts | 30 | 13FC+35 | 38;39;40 |  | R11: 1; R12: 2
21 |  | Procurement documents | 70 | 13 | 23;24;25;27;28;30;31;33;34;35;36;38;39;40 |  | R11: 1; R12: 2
23 |  | Site preparation | 25 | 15;16;17;21 | 24
24 |  | Sanitary Water system | 18 | 19;21;23 | 25
25 |  | Electrical system | 43 | 19;21;24 | 27;28
27 |  | Soccer field | 36 | 19;21;25 | 28
28 |  | Changing rooms & toilettes | 39 | 19;21;25;27 | 30
30 |  | Gym | 15 | 19;21;28 | 31
31 |  | Leisure area | 7 | 19;21;30 | 33
33 |  | Garden | 10 | 19;21;31 | 34;38
34 |  | Roads | 10 | 19;21;33 | 35;36;38
35 |  | Decorative elements | 5 | 19;21;34 | 38
36 |  | Lagoon | 60 | 19;21;34 | 38
38 |  | Urban metallic components installment | 22 | 20;21;33;34;35;36 | 39
39 |  | Soccer field and leisure zone components installment | 15 | 20;21;38 | 40
40 |  | Installation of water dispensers | 15 | 20;21;39 | 42
42 |  | Equipment functionality test | 15 | 40 | 43 |  | R1: 1; R2: 1; R3: 1; R4: 1; R8: 2; R9: 1
43 |  | Final test supporting document | 10 | 42 | 44 |  | R3: 2; R4: 3; R8: 1; R9: 1
44 |  | Operations manual | 5 | 43;6 | 46 | bar: R3 to R4; R8 to R9
46 |  | Contracts closure | 3 | 44 | 47 | bar: R6; R10 to R12
47 |  | Project closing report | 1 | 46 | 48 | bar: R6
48 |  | ACCEPTANCE Project 1 | 0 | 47

## P3
ID | Section | Name | Duration | Predecessors | Successors | Pred other projects | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
3 |  | Contract signing | 0 |  | 5
5 |  | Project planning | 40 | 3 | 6;8 | bar: R7
6 |  | Project execution and controlling | 600 | 5 | 46 | bar: R7
8 |  | Area survey | 15 | 5 | 9FC+5;11 |  | R1: 3; R2: 2; R3: 2; R4: 3
9 |  | Topographic study | 8 | 8FC+5 | 10 |  | R1: 2; R2: 3
10 |  | Conceptual design | 8 | 9 | 11 |  | R1: 3; R2: 5; R3: 2; R4: 4
11 |  | Architectural design | 15 | 10;8 | 13;18 |  | R1: 3; R2: 5; R3: 2; R4: 4
13 |  | Bidding | 32 | 11 | 20;34;29;14 |  | R1: 1; R2: 1; R3: 1; R4: 1; R11: 1; R12: 2
14 |  | Equipment contracts | 14 | 13 | 38;39;40;16 |  | R1: 1; R2: 1; R3: 1; R4: 1; R11: 1; R12: 2
16 |  | Legal permits | 15 | 14 | 20;17 |  | R10: 2
17 |  | Construction license | 15 | 16 | 20 |  | R1: 1; R3: 1; R10: 2
18 |  | Operations licenses | 15 | 11 | 45 |  | R1: 1; R3: 1; R10: 2
20 |  | Existing structure demolition | 10 | 16;17;13 | 21
21 |  | Debris removal | 10 | 20 | 22
22 |  | Earthmoving works | 15 | 21 | 23
23 |  | Foundations | 15 | 22 | 24
24 |  | Reinforced concrete structure | 15 | 23 | 25
25 |  | Vertical walls | 60 | 24 | 26
26 |  | Thermo-acoustic insulation | 30 | 25 | 27
27 |  | Walls plaster | 20 | 26 | 29
29 |  | Sanitary water system | 42 | 13;27 | 30
30 |  | Pipeline system | 42 | 29 | 31
31 |  | Electrical system | 28 | 30 | 32;38
32 |  | Mechanical system | 42 | 31 | 34;38
34 |  | Floor covering | 30 | 13;32 | 35
35 |  | Windows and doors placement | 30 | 34 | 36
36 |  | Wall patching | 45 | 35 | 37
37 |  | Painting walls | 50 | 36 | 38;39
38 |  | Electrical appliances installment | 60 | 14;37;32;31 | 39
39 |  | Sanitary facilities installment | 70 | 38;14;37 | 40;42
40 |  | Furnitures | 50 | 39;14 | 43;42
42 |  | Equipment functionality test | 15 | 39;40 | 43 |  | R1: 1; R3: 1; R8: 2; R9: 1
43 |  | Equipment installment acceptance | 15 | 42;40 | 44 |  | R1: 2; R3: 2; R8: 2; R9: 1
44 |  | Building site final cleaning | 10 | 43 | 45 | bar: R8 to R9
45 |  | Final test supporting document | 10 | 18;44 | 46 |  | R4: 2; R8: 2; R9: 1
46 |  | Operations manual | 10 | 45;6 | 48 |  | R3: 2; R4: 1; R8: 2; R9: 1
48 |  | Contracts closure | 20 | 46 | 49 |  | R3: 1; R4: 2; R7: 1; R10: 2; R11: 1; R12: 2
49 |  | Project closing report | 30 | 48 | 50 | bar: R7
50 |  | ACCEPTANCE Project 1 | 0 | 49

## Resources
ID | Name | Type | Units
R1 | Architect Sr | HC | 3
R2 | Architect Jr | HC | 5
R3 | Engineer Sr | HC | 2
R4 | Engineer Jr | HC | 4
R5 | PM 1 | HC | 1
R6 | PM 2 | HC | 1
R7 | PM 3 | HC | 1
R8 | Quality Manager Sr | HC | 2
R9 | Quality Manager Jr | HC | 1
R10 | Lawyer and Legal Specialist | HC | 2
R11 | Procurement Manager | HC | 1
R12 | Procurement Assistant | HC | 2