## P1_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
2 | Contract signing | 0 | 0 | 0 |  | 3
3 | Project planning | 30 | 0 | 30 | 2 | 4, 5
4 | Project execution and controlling | 159 | 30 | 189 | 3 | 56
5 | Conceptual design | 5 | 30 | 35 | 3 | 6
6 | Functional requirements definition | 5 | 35 | 40 | 5 | 7, 8, 9
7 | Zone 1 design | 8 | 40 | 48 | 6 | 10, 11, 12, 13, 14
8 | Zone 2 design | 8 | 48 | 56 | 6 | 10, 11, 12, 13, 29
9 | Zone 3 design | 8 | 56 | 64 | 6 | 10, 11, 12, 13
10 | Construction tramits | 30 | 64 | 94 | 7, 8, 9 | 14, 29, 54
11 | Operations licenses | 25 | 64 | 89 | 7, 8, 9 | 54
12 | Insurance contract | 9 | 89 | 98 | 7, 8, 9 | 54
13 | Bidding | 15 | 64 | 79 | 7, 8, 9 | 14, 15, 16, 29, 30, 31, 42, 43, 41
14 | Pipeline system zone 1 | 7 | 94 | 101 | 7, 10, 13 | 15, 23
29 | Pipeline system zone 2 | 6 | 94 | 100 | 8, 10, 13 | 30
15 | Electrical system zone 1 | 10 | 101 | 111 | 13, 14 | 17, 18, 19, 20, 21, 16
30 | Electrical system zone 2 | 9 | 100 | 109 | 13, 29 | 32, 31, 33
20 | Installation of stair | 7 | 111 | 118 | 15 | 21
16 | Air Condition System zone 1 | 5 | 111 | 116 | 13, 15 | 17
31 | Air Condition System zone 2 | 5 | 109 | 114 | 13, 30 | 32
33 | Installation electrical stair | 14 | 109 | 123 | 30 | 35
21 | Elevator replacement | 7 | 118 | 125 | 15, 20 | 22
17 | Floor adaptation zone 1 | 3 | 116 | 119 | 15, 16 | 18
32 | Floor adaptation zone 2 | 3 | 114 | 117 | 30, 31 | 34, 35, 36FC+8
22 | Installation of turnstiles for employee entry | 2 | 125 | 127 | 21 | 23
18 | Installation of mirrors | 2 | 119 | 121 | 15, 17 | 19
34 | Replacement of toilets zone 2 | 8 | 117 | 125 | 32 | 35
36 | Installation of fiber optics for WiFi zone 2 | 3 | 125 | 128 | 32FC+8 | 37
23 | Installation of fiber optics for WiFi zone 1 | 1 | 127 | 128 | 22, 14 | 24
19 | Replacement of toilets zone 1 | 5 | 121 | 126 | 15, 18 | 25
35 | Elevator door adaptation | 3 | 125 | 128 | 34, 32, 33 | 37
24 | Installation of water dispensers | 1 | 128 | 129 | 23 | 25
37 | Wall patching on floor zone 2 | 8 | 128 | 136 | 36, 35 | 38FC+5
25 | Wall patching on floor 1 | 8 | 129 | 137 | 24, 19 | 26FC+5
38 | Painting walls on floor zone 2 | 5 | 141 | 146 | 37FC+5 | 39, 40
26 | Painting walls on floor 1 | 5 | 142 | 147 | 25FC+5 | 27, 28
39 | Nurses room adaptation | 3 | 146 | 149 | 38 | 53
40 | Medical consultancy rooms | 8 | 146 | 154 | 38 | 41, 53
27 | Adaptation and installation of machinary | 6 | 147 | 153 | 26 | 28
41 | Pipeline system zone 3 | 6 | 154 | 160 | 40, 13 | 42, 46, 47
28 | Furniture installation | 2 | 153 | 155 | 26, 27 | 53
42 | Electrical system zone 3 | 9 | 160 | 169 | 13, 41 | 43, 45FC+5, 47
43 | Air Condition System zone 3 | 5 | 169 | 174 | 13, 42 | 44
45 | Elevator door adaptation | 2 | 174 | 176 | 42FC+5 | 48
47 | Industrial kitchen installment | 10 | 169 | 179 | 41, 42 | 48
44 | Replacement of toilets zone 3 | 3 | 174 | 177 | 43 | 46
46 | Installation of fiber optics for WiFi zone 3 | 2 | 177 | 179 | 41, 44 | 48
48 | Wall patching on floor zone 3 | 8 | 179 | 187 | 46, 45, 47 | 49FC+5
49 | Painting walls on floor zone 3 | 5 | 192 | 197 | 48FC+5 | 50, 51, 52FC+2
50 | Clients room adaptation | 3 | 197 | 200 | 49 | 53
51 | Dining room adaptation | 3 | 197 | 200 | 49 | 53
52 | Control Center installment | 1 | 199 | 200 | 49FC+2 | 53
53 | Equipment functionality test | 3 | 200 | 203 | 28, 40, 52, 39, 50, 51 | 54
54 | Final test supporting document | 1 | 203 | 204 | 10, 11, 12, 53 | 55
55 | Operations manual | 1 | 204 | 205 | 54 | 56
56 | Contracts closure | 3 | 205 | 208 | 4, 55 | 57
57 | Project closing report | 1 | 208 | 209 | 56 | 58
58 | ACCEPTANCE Project 1 | 0 | 209 | 209 | 57

## P1_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
2 | Contract signing | 0 | 0 | 0 |  | 3
3 | Project planning | 30 | 0 | 30 | 2 | 4, 5
4 | Project execution and controlling | 159 | 30 | 189 | 3 | 56
5 | Conceptual design | 5 | 30 | 35 | 3 | 6
6 | Functional requirements definition | 5 | 35 | 40 | 5 | 7, 8, 9
7 | Zone 1 design | 8 | 40 | 48 | 6 | 10, 11, 12, 13, 14
8 | Zone 2 design | 8 | 40 | 48 | 6 | 10, 11, 12, 13, 29
9 | Zone 3 design | 8 | 40 | 48 | 6 | 10, 11, 12, 13
10 | Construction tramits | 30 | 48 | 78 | 7, 8, 9 | 14, 29, 54
11 | Operations licenses | 25 | 48 | 73 | 7, 8, 9 | 54
12 | Insurance contract | 9 | 48 | 57 | 7, 8, 9 | 54
13 | Bidding | 15 | 48 | 63 | 7, 8, 9 | 14, 15, 16, 29, 30, 31, 42, 43, 41
14 | Pipeline system zone 1 | 7 | 78 | 85 | 7, 10, 13 | 15, 23
29 | Pipeline system zone 2 | 6 | 78 | 84 | 8, 10, 13 | 30
15 | Electrical system zone 1 | 10 | 85 | 95 | 13, 14 | 17, 18, 19, 20, 21, 16
30 | Electrical system zone 2 | 9 | 84 | 93 | 13, 29 | 32, 31, 33
20 | Installation of stair | 7 | 95 | 102 | 15 | 21
16 | Air Condition System zone 1 | 5 | 95 | 100 | 13, 15 | 17
31 | Air Condition System zone 2 | 5 | 93 | 98 | 13, 30 | 32
33 | Installation electrical stair | 14 | 93 | 107 | 30 | 35
21 | Elevator replacement | 7 | 102 | 109 | 15, 20 | 22
17 | Floor adaptation zone 1 | 3 | 100 | 103 | 15, 16 | 18
32 | Floor adaptation zone 2 | 3 | 98 | 101 | 30, 31 | 34, 35, 36FC+8
22 | Installation of turnstiles for employee entry | 2 | 109 | 111 | 21 | 23
18 | Installation of mirrors | 2 | 103 | 105 | 15, 17 | 19
34 | Replacement of toilets zone 2 | 8 | 101 | 109 | 32 | 35
36 | Installation of fiber optics for WiFi zone 2 | 3 | 109 | 112 | 32FC+8 | 37
23 | Installation of fiber optics for WiFi zone 1 | 1 | 111 | 112 | 22, 14 | 24
19 | Replacement of toilets zone 1 | 5 | 105 | 110 | 15, 18 | 25
35 | Elevator door adaptation | 3 | 109 | 112 | 34, 32, 33 | 37
24 | Installation of water dispensers | 1 | 112 | 113 | 23 | 25
37 | Wall patching on floor zone 2 | 8 | 112 | 120 | 36, 35 | 38FC+5
25 | Wall patching on floor 1 | 8 | 113 | 121 | 24, 19 | 26FC+5
38 | Painting walls on floor zone 2 | 5 | 125 | 130 | 37FC+5 | 39, 40
26 | Painting walls on floor 1 | 5 | 126 | 131 | 25FC+5 | 27, 28
39 | Nurses room adaptation | 3 | 130 | 133 | 38 | 53
40 | Medical consultancy rooms | 8 | 130 | 138 | 38 | 41, 53
27 | Adaptation and installation of machinary | 6 | 131 | 137 | 26 | 28
41 | Pipeline system zone 3 | 6 | 138 | 144 | 40, 13 | 42, 46, 47
28 | Furniture installation | 2 | 137 | 139 | 26, 27 | 53
42 | Electrical system zone 3 | 9 | 144 | 153 | 13, 41 | 43, 45FC+5, 47
43 | Air Condition System zone 3 | 5 | 153 | 158 | 13, 42 | 44
45 | Elevator door adaptation | 2 | 158 | 160 | 42FC+5 | 48
47 | Industrial kitchen installment | 10 | 153 | 163 | 41, 42 | 48
44 | Replacement of toilets zone 3 | 3 | 158 | 161 | 43 | 46
46 | Installation of fiber optics for WiFi zone 3 | 2 | 161 | 163 | 41, 44 | 48
48 | Wall patching on floor zone 3 | 8 | 163 | 171 | 46, 45, 47 | 49FC+5
49 | Painting walls on floor zone 3 | 5 | 176 | 181 | 48FC+5 | 50, 51, 52FC+2
50 | Clients room adaptation | 3 | 181 | 184 | 49 | 53
51 | Dining room adaptation | 3 | 181 | 184 | 49 | 53
52 | Control Center installment | 1 | 183 | 184 | 49FC+2 | 53
53 | Equipment functionality test | 3 | 184 | 187 | 28, 40, 52, 39, 50, 51 | 54
54 | Final test supporting document | 1 | 187 | 188 | 10, 11, 12, 53 | 55
55 | Operations manual | 1 | 188 | 189 | 54 | 56
56 | Contracts closure | 3 | 189 | 192 | 4, 55 | 57
57 | Project closing report | 1 | 192 | 193 | 56 | 58
58 | ACCEPTANCE Project 1 | 0 | 193 | 193 | 57

## P2_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 60 | 0 | 60 | 3 | 6, 8
6 | Project execution and controlling | 516 | 60 | 576 | 5 | 44
8 | Documentation analysis | 30 | 60 | 90 | 5 | 9
9 | Consultation results report | 30 | 90 | 120 | 8 | 11, 12FC+5
11 | Architectural design | 20 | 120 | 140 | 9 | 13
12 | Lanscape design | 15 | 125 | 140 | 9FC+5 | 13
13 | Final design | 20 | 140 | 160 | 11, 12 | 15, 16, 17, 19FC+20, 20FC+35, 21
15 | Legal permits | 30 | 160 | 190 | 13 | 23
16 | Environmental permits | 30 | 190 | 220 | 13 | 23
17 | Construction license | 30 | 220 | 250 | 13 | 23
19 | Providers contracts | 45 | 180 | 225 | 13FC+20 | 24, 25, 27, 28, 30, 31, 33, 34, 35, 36
20 | Components contracts | 30 | 225 | 255 | 13FC+35 | 38, 39, 40
21 | Procurement documents | 70 | 255 | 325 | 13 | 23, 24, 25, 27, 28, 30, 31, 33, 34, 35, 36, 38, 39, 40
23 | Site preparation | 25 | 325 | 350 | 15, 16, 17, 21 | 24
24 | Sanitary Water system | 18 | 350 | 368 | 19, 21, 23 | 25
25 | Electrical system | 43 | 368 | 411 | 19, 21, 24 | 27, 28
27 | Soccer field | 36 | 411 | 447 | 19, 21, 25 | 28
28 | Changing rooms & toilettes | 39 | 447 | 486 | 19, 21, 25, 27 | 30
30 | Gym | 15 | 486 | 501 | 19, 21, 28 | 31
31 | Leisure area | 7 | 501 | 508 | 19, 21, 30 | 33
33 | Garden | 10 | 508 | 518 | 19, 21, 31 | 34, 38
34 | Roads | 10 | 518 | 528 | 19, 21, 33 | 35, 36, 38
35 | Decorative elements | 5 | 528 | 533 | 19, 21, 34 | 38
36 | Lagoon | 60 | 528 | 588 | 19, 21, 34 | 38
38 | Urban metallic components installment | 22 | 588 | 610 | 20, 21, 33, 34, 35, 36 | 39
39 | Soccer field and leisure zone components installment | 15 | 610 | 625 | 20, 21, 38 | 40
40 | Installation of water dispensers | 15 | 625 | 640 | 20, 21, 39 | 42
42 | Equipment functionality test | 15 | 640 | 655 | 40 | 43
43 | Final test supporting document | 10 | 655 | 665 | 42 | 44
44 | Operations manual | 5 | 665 | 670 | 43, 6 | 46
46 | Contracts closure | 3 | 670 | 673 | 44 | 47
47 | Project closing report | 1 | 673 | 674 | 46 | 48
48 | ACCEPTANCE Project 1 | 0 | 674 | 674 | 47

## P2_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 60 | 0 | 60 | 3 | 6, 8
6 | Project execution and controlling | 516 | 60 | 576 | 5 | 44
8 | Documentation analysis | 30 | 60 | 90 | 5 | 9
9 | Consultation results report | 30 | 90 | 120 | 8 | 11, 12FC+5
11 | Architectural design | 20 | 120 | 140 | 9 | 13
12 | Lanscape design | 15 | 125 | 140 | 9FC+5 | 13
13 | Final design | 20 | 140 | 160 | 11, 12 | 15, 16, 17, 19FC+20, 20FC+35, 21
15 | Legal permits | 30 | 160 | 190 | 13 | 23
16 | Environmental permits | 30 | 160 | 190 | 13 | 23
17 | Construction license | 30 | 160 | 190 | 13 | 23
19 | Providers contracts | 45 | 180 | 225 | 13FC+20 | 24, 25, 27, 28, 30, 31, 33, 34, 35, 36
20 | Components contracts | 30 | 195 | 225 | 13FC+35 | 38, 39, 40
21 | Procurement documents | 70 | 160 | 230 | 13 | 23, 24, 25, 27, 28, 30, 31, 33, 34, 35, 36, 38, 39, 40
23 | Site preparation | 25 | 230 | 255 | 15, 16, 17, 21 | 24
24 | Sanitary Water system | 18 | 255 | 273 | 19, 21, 23 | 25
25 | Electrical system | 43 | 273 | 316 | 19, 21, 24 | 27, 28
27 | Soccer field | 36 | 316 | 352 | 19, 21, 25 | 28
28 | Changing rooms & toilettes | 39 | 352 | 391 | 19, 21, 25, 27 | 30
30 | Gym | 15 | 391 | 406 | 19, 21, 28 | 31
31 | Leisure area | 7 | 406 | 413 | 19, 21, 30 | 33
33 | Garden | 10 | 413 | 423 | 19, 21, 31 | 34, 38
34 | Roads | 10 | 423 | 433 | 19, 21, 33 | 35, 36, 38
35 | Decorative elements | 5 | 433 | 438 | 19, 21, 34 | 38
36 | Lagoon | 60 | 433 | 493 | 19, 21, 34 | 38
38 | Urban metallic components installment | 22 | 493 | 515 | 20, 21, 33, 34, 35, 36 | 39
39 | Soccer field and leisure zone components installment | 15 | 515 | 530 | 20, 21, 38 | 40
40 | Installation of water dispensers | 15 | 530 | 545 | 20, 21, 39 | 42
42 | Equipment functionality test | 15 | 545 | 560 | 40 | 43
43 | Final test supporting document | 10 | 560 | 570 | 42 | 44
44 | Operations manual | 5 | 576 | 581 | 43, 6 | 46
46 | Contracts closure | 3 | 581 | 584 | 44 | 47
47 | Project closing report | 1 | 584 | 585 | 46 | 48
48 | ACCEPTANCE Project 1 | 0 | 585 | 585 | 47

## P3_Constrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 40 | 0 | 40 | 3 | 6, 8
6 | Project execution and controlling | 600 | 40 | 640 | 5 | 46
8 | Area survey | 15 | 40 | 55 | 5 | 9FC+5, 11
9 | Topographic study | 8 | 60 | 68 | 8FC+5 | 10
10 | Conceptual design | 8 | 68 | 76 | 9 | 11
11 | Architectural design | 15 | 76 | 91 | 10, 8 | 13, 18
13 | Bidding | 32 | 91 | 123 | 11 | 20, 34, 29, 14
18 | Operations licenses | 15 | 91 | 106 | 11 | 45
14 | Equipment contracts | 14 | 123 | 137 | 13 | 38, 39, 40, 16
16 | Legal permits | 15 | 137 | 152 | 14 | 20, 17
17 | Construction license | 15 | 152 | 167 | 16 | 20
20 | Existing structure demolition | 10 | 167 | 177 | 16, 17, 13 | 21
21 | Debris removal | 10 | 177 | 187 | 20 | 22
22 | Earthmoving works | 15 | 187 | 202 | 21 | 23
23 | Foundations | 15 | 202 | 217 | 22 | 24
24 | Reinforced concrete structure | 15 | 217 | 232 | 23 | 25
25 | Vertical walls | 60 | 232 | 292 | 24 | 26
26 | Thermo-acoustic insulation | 30 | 292 | 322 | 25 | 27
27 | Walls plaster | 20 | 322 | 342 | 26 | 29
29 | Sanitary water system | 42 | 342 | 384 | 13, 27 | 30
30 | Pipeline system | 42 | 384 | 426 | 29 | 31
31 | Electrical system | 28 | 426 | 454 | 30 | 32, 38
32 | Mechanical system | 42 | 454 | 496 | 31 | 34, 38
34 | Floor covering | 30 | 496 | 526 | 13, 32 | 35
35 | Windows and doors placement | 30 | 526 | 556 | 34 | 36
36 | Wall patching | 45 | 556 | 601 | 35 | 37
37 | Painting walls | 50 | 601 | 651 | 36 | 38, 39
38 | Electrical appliances installment | 60 | 651 | 711 | 14, 37, 32, 31 | 39
39 | Sanitary facilities installment | 70 | 711 | 781 | 38, 14, 37 | 40, 42
40 | Furnitures | 50 | 781 | 831 | 39, 14 | 43, 42
42 | Equipment functionality test | 15 | 831 | 846 | 39, 40 | 43
43 | Equipment installment acceptance | 15 | 846 | 861 | 42, 40 | 44
44 | Building site final cleaning | 10 | 861 | 871 | 43 | 45
45 | Final test supporting document | 10 | 871 | 881 | 18, 44 | 46
46 | Operations manual | 10 | 881 | 891 | 45, 6 | 48
48 | Contracts closure | 20 | 891 | 911 | 46 | 49
49 | Project closing report | 30 | 911 | 941 | 48 | 50
50 | ACCEPTANCE Project 1 | 0 | 941 | 941 | 49

## P3_notConstrained
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 40 | 0 | 40 | 3 | 6, 8
6 | Project execution and controlling | 600 | 40 | 640 | 5 | 46
8 | Area survey | 15 | 40 | 55 | 5 | 9FC+5, 11
9 | Topographic study | 8 | 60 | 68 | 8FC+5 | 10
10 | Conceptual design | 8 | 68 | 76 | 9 | 11
11 | Architectural design | 15 | 76 | 91 | 10, 8 | 13, 18
13 | Bidding | 32 | 91 | 123 | 11 | 20, 34, 29, 14
18 | Operations licenses | 15 | 91 | 106 | 11 | 45
14 | Equipment contracts | 14 | 123 | 137 | 13 | 38, 39, 40, 16
16 | Legal permits | 15 | 137 | 152 | 14 | 20, 17
17 | Construction license | 15 | 152 | 167 | 16 | 20
20 | Existing structure demolition | 10 | 167 | 177 | 16, 17, 13 | 21
21 | Debris removal | 10 | 177 | 187 | 20 | 22
22 | Earthmoving works | 15 | 187 | 202 | 21 | 23
23 | Foundations | 15 | 202 | 217 | 22 | 24
24 | Reinforced concrete structure | 15 | 217 | 232 | 23 | 25
25 | Vertical walls | 60 | 232 | 292 | 24 | 26
26 | Thermo-acoustic insulation | 30 | 292 | 322 | 25 | 27
27 | Walls plaster | 20 | 322 | 342 | 26 | 29
29 | Sanitary water system | 42 | 342 | 384 | 13, 27 | 30
30 | Pipeline system | 42 | 384 | 426 | 29 | 31
31 | Electrical system | 28 | 426 | 454 | 30 | 32, 38
32 | Mechanical system | 42 | 454 | 496 | 31 | 34, 38
34 | Floor covering | 30 | 496 | 526 | 13, 32 | 35
35 | Windows and doors placement | 30 | 526 | 556 | 34 | 36
36 | Wall patching | 45 | 556 | 601 | 35 | 37
37 | Painting walls | 50 | 601 | 651 | 36 | 38, 39
38 | Electrical appliances installment | 60 | 651 | 711 | 14, 37, 32, 31 | 39
39 | Sanitary facilities installment | 70 | 711 | 781 | 38, 14, 37 | 40, 42
40 | Furnitures | 50 | 781 | 831 | 39, 14 | 43, 42
42 | Equipment functionality test | 15 | 831 | 846 | 39, 40 | 43
43 | Equipment installment acceptance | 15 | 846 | 861 | 42, 40 | 44
44 | Building site final cleaning | 10 | 861 | 871 | 43 | 45
45 | Final test supporting document | 10 | 871 | 881 | 18, 44 | 46
46 | Operations manual | 10 | 881 | 891 | 45, 6 | 48
48 | Contracts closure | 20 | 891 | 911 | 46 | 49
49 | Project closing report | 30 | 911 | 941 | 48 | 50
50 | ACCEPTANCE Project 1 | 0 | 941 | 941 | 49