## P1
ID | Section | Name | Duration | Predecessors | Successors | External Predecessors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
2 | Pre-Construction | Contract signing | 0 |  | 3 | bar: R5
3 | Pre-Construction | Project planning | 30 | 2 | 4;5 | bar: R5
4 | Pre-Construction | Project execution and controlling | 150 | 3 | 56 | bar: R5
5 | Pre-Construction | Conceptual design | 5 | 3 | 6 |  | R1: 2; R2: 2
6 | Pre-Construction | Functional requirements definition | 5 | 5 | 7;8;9 | bar: R1 to R2
7 | Pre-Construction | Zone 1 design | 8 | 6 | 10;11;12;13;14 |  | R1: 2; R2: 3
8 | Pre-Construction | Zone 2 design | 8 | 6 | 10;11;12;13;29 |  | R1: 2; R2: 3
9 | Pre-Construction | Zone 3 design | 8 | 6 | 10;11;12;13 |  | R1: 2; R2: 3
10 | Pre-Construction | Construction tramits | 30 | 7;8;9 | 14;29;54 | bar: R10
11 | Pre-Construction | Operations licenses | 25 | 7;8;9 | 54 | bar: R10
12 | Pre-Construction | Insurance contract | 9 | 7;8;9 | 54 | bar: R10
13 | Pre-Construction | Bidding | 15 | 7;8;9 | 14;15;16;29;30;31;42;43;41 | bar: R11
14 | Construction | Pipeline system zone 1 | 7 | 7;10;13 | 15;23 | P2-9; P3-8 | bar: R12
15 | Construction | Electrical system zone 1 | 10 | 13;14 | 17;18;19;20;21;16
16 | Construction | Air Condition System zone 1 | 5 | 13;15 | 17
17 | Construction | Floor adaptation zone 1 | 3 | 15;16 | 18
18 | Construction | Installation of mirrors | 2 | 15;17 | 19
19 | Construction | Replacement of toilets zone 1 | 5 | 15;18 | 25
20 | Construction | Installation of stair | 7 | 15 | 21
21 | Construction | Elevator replacement | 7 | 15;20 | 22
22 | Construction | Installation of turnstiles for employee entry | 2 | 21 | 23
23 | Construction | Installation of fiber optics for WiFi zone 1 | 1 | 22;14 | 24
24 | Construction | Installation of water dispensers | 1 | 23 | 25
25 | Construction | Wall patching on floor 1 | 8 | 24;19 | 26FC+5
26 | Construction | Painting walls on floor 1 | 5 | 25FC+5 | 27;28
27 | Construction | Adaptation and installation of machinary | 6 | 26 | 28
28 | Construction | Furniture installation | 2 | 26;27 | 53
29 | Construction | Pipeline system zone 2 | 6 | 8;10;13 | 30
30 | Construction | Electrical system zone 2 | 9 | 13;29 | 32;31;33
31 | Construction | Air Condition System zone 2 | 5 | 13;30 | 32
32 | Construction | Floor adaptation zone 2 | 3 | 30;31 | 34;35;36FC+8
33 | Construction | Installation electrical stair | 14 | 30 | 35
34 | Construction | Replacement of toilets zone 2 | 8 | 32 | 35
35 | Construction | Elevator door adaptation | 3 | 34;32;33 | 37
36 | Construction | Installation of fiber optics for WiFi zone 2 | 3 | 32FC+8 | 37
37 | Construction | Wall patching on floor zone 2 | 8 | 36;35 | 38FC+5
38 | Construction | Painting walls on floor zone 2 | 5 | 37FC+5 | 39;40
39 | Construction | Nurses room adaptation | 3 | 38 | 53
40 | Construction | Medical consultancy rooms | 8 | 38 | 41;53
41 | Construction | Pipeline system zone 3 | 6 | 40;13 | 42;46;47
42 | Construction | Electrical system zone 3 | 9 | 13;41 | 43;45FC+5;47
43 | Construction | Air Condition System zone 3 | 5 | 13;42 | 44
44 | Construction | Replacement of toilets zone 3 | 3 | 43 | 46
45 | Construction | Elevator door adaptation | 2 | 42FC+5 | 48
46 | Construction | Installation of fiber optics for WiFi zone 3 | 2 | 41;44 | 48
47 | Construction | Industrial kitchen installment | 10 | 41;42 | 48
48 | Construction | Wall patching on floor zone 3 | 8 | 46;45;47 | 49FC+5
49 | Construction | Painting walls on floor zone 3 | 5 | 48FC+5 | 50;51;52FC+2
50 | Construction | Clients room adaptation | 3 | 49 | 53
51 | Construction | Dining room adaptation | 3 | 49 | 53
52 | Construction | Control Center installment | 1 | 49FC+2 | 53
53 | Construction | Equipment functionality test | 3 | 28;40;52;39;50;51 | 54 | bar: R1; R3; R8 to R9
54 | Construction | Final test supporting document | 1 | 10;11;12;53 | 55 | bar: R4; R8 to R9
55 | Construction | Operations manual | 1 | 54 | 56 | bar: R8 to R9
56 | Post-Contruction | Contracts closure | 3 | 4;55 | 57 | bar: R5; R10 to R12
57 | Post-Contruction | Project closing report | 1 | 56 | 58 | bar: R5
58 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 57

## P2
ID | Section | Name | Duration | Predecessors | Successors | External Predecessors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
2 | Pre-Construction | Contract signing | 0 |  | 3
3 | Pre-Construction | Project planning | 60 | 2 | 4;5 | bar: R6
4 | Pre-Construction | Project execution and controlling | 500 | 3 | 33 | bar: R6
5 | Pre-Construction | Documentation analysis | 30 | 3 | 6 |  | R1: 2; R2: 2
6 | Pre-Construction | Consultation results report | 30 | 5 | 7;8FC+5 | bar: R1 to R4
7 | Pre-Construction | Architectural design | 20 | 6 | 9 |  | R1: 1; R3: 2
8 | Pre-Construction | Lanscape design | 15 | 6FC+5 | 9 |  | R1: 1; R2: 2
9 | Pre-Construction | Final design | 20 | 7;8 | 10;11;12;13FC+20;14FC+35;15 |  | R1: 1; R2: 3; R3: 2; R4: 2
10 | Pre-Construction | Legal permits | 30 | 9 | 16 |  | R10: 2
11 | Pre-Construction | Environmental permits | 30 | 9 | 16 | bar: R10
12 | Pre-Construction | Construction license | 30 | 9 | 16 |  | R10: 2
13 | Pre-Construction | Providers contracts | 45 | 9FC+20 | 17;18;19;20;21;22;23;24;25;26 |  | R11: 1; R12: 2
14 | Pre-Construction | Components contracts | 30 | 9FC+35 | 27;28;29 |  | R11: 1; R12: 2
15 | Pre-Construction | Procurement documents | 70 | 9 | 16;17;18;19;20;21;22;23;24;25;26;27;28;29 |  | R11: 1; R12: 2
16 | Construction | Site preparation | 25 | 10;11;12;15 | 17 | P1-7; P1-8; P1-9; P3-8
17 | Construction | Sanitary Water system | 18 | 13;15;16 | 18
18 | Construction | Electrical system | 43 | 13;15;17 | 19;20
19 | Construction | Soccer field | 36 | 13;15;18 | 20
20 | Construction | Changing rooms & toilettes | 39 | 13;15;18;19 | 21
21 | Construction | Gym | 15 | 13;15;20 | 22
22 | Construction | Leisure area | 7 | 13;15;21 | 23
23 | Construction | Garden | 10 | 13;15;22 | 24;27
24 | Construction | Roads | 10 | 13;15;23 | 25;26;27
25 | Construction | Decorative elements | 5 | 13;15;24 | 27
26 | Construction | Lagoon | 60 | 13;15;24 | 27
27 | Construction | Urban metallic components installment | 22 | 14;15;23;24;25;26 | 28
28 | Construction | Soccer field and leisure zone components installment | 15 | 14;15;27 | 29
29 | Construction | Installation of water dispensers | 15 | 14;15;28 | 30
30 | Construction | Equipment functionality test | 15 | 29 | 31 |  | R1: 1; R2: 1; R3: 1; R4: 1; R8: 2; R9: 1
31 | Construction | Final test supporting document | 10 | 30 | 32 |  | R3: 2; R4: 3; R8: 1; R9: 1
32 | Construction | Operations manual | 5 | 31 | 33 | bar: R3 to R4; R8 to R9
33 | Post-Contruction | Contracts closure | 3 | 32;4 | 34 | bar: R6; R10 to R12
34 | Post-Contruction | Project closing report | 1 | 33 | 35 | bar: R6
35 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 34

## P3
ID | Section | Name | Duration | Predecessors | Successors | External Predecessors | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12
2 | Pre-Construction | Contract signing | 0 |  | 3
3 | Pre-Construction | Project planning | 40 | 2 | 4;5 | bar: R7
4 | Pre-Construction | Project execution and controlling | 850 | 3 | 38 | bar: R7
5 | Pre-Construction | Area survey | 15 | 3 | 6FC+5;8 |  | R1: 3; R2: 2; R3: 2; R4: 3
6 | Pre-Construction | Topographic study | 8 | 5FC+5 | 7 |  | R1: 2; R2: 3
7 | Pre-Construction | Conceptual design | 8 | 6 | 8 |  | R1: 3; R2: 5; R3: 2; R4: 4
8 | Pre-Construction | Architectural design | 15 | 7;5 | 9;13 |  | R1: 3; R2: 5; R3: 2; R4: 4
9 | Pre-Construction | Bidding | 32 | 8 | 14;26;22;10 |  | R1: 1; R2: 1; R3: 1; R4: 1; R11: 1; R12: 2
10 | Pre-Construction | Equipment contracts | 14 | 9 | 30;31;32;11 |  | R1: 1; R2: 1; R3: 1; R4: 1; R11: 1; R12: 2
11 | Pre-Construction | Legal permits | 15 | 10 | 14;12 |  | R10: 2
12 | Pre-Construction | Construction license | 15 | 11 | 14 |  | R1: 1; R3: 1; R10: 2
13 | Pre-Construction | Operations licenses | 15 | 8 | 36 |  | R1: 1; R3: 1; R10: 2
14 | Construction | Existing structure demolition | 10 | 11;12;9 | 15 | P1-7; P1-8; P1-9; P2-9
15 | Construction | Debris removal | 10 | 14 | 16
16 | Construction | Earthmoving works | 15 | 15 | 17
17 | Construction | Foundations | 15 | 16 | 18
18 | Construction | Reinforced concrete structure | 15 | 17 | 19
19 | Construction | Vertical walls | 60 | 18 | 20
20 | Construction | Thermo-acoustic insulation | 30 | 19 | 21
21 | Construction | Walls plaster | 20 | 20 | 22
22 | Construction | Sanitary water system | 42 | 9;21 | 23
23 | Construction | Pipeline system | 42 | 22 | 24
24 | Construction | Electrical system | 28 | 23 | 25;30
25 | Construction | Mechanical system | 42 | 24 | 26;30
26 | Construction | Floor covering | 30 | 9;25 | 27
27 | Construction | Windows and doors placement | 30 | 26 | 28
28 | Construction | Wall patching | 45 | 27 | 29
29 | Construction | Painting walls | 50 | 28 | 30;31
30 | Construction | Electrical appliances installment | 60 | 10;29;25;24 | 31
31 | Construction | Sanitary facilities installment | 70 | 30;10;29 | 32;33
32 | Construction | Furnitures | 50 | 31;10 | 34;33
33 | Construction | Equipment functionality test | 15 | 31;32 | 34 |  | R1: 1; R3: 1; R8: 2; R9: 1
34 | Construction | Equipment installment acceptance | 15 | 33;32 | 35 |  | R1: 2; R3: 2; R8: 2; R9: 1
35 | Construction | Building site final cleaning | 10 | 34 | 36 | bar: R8 to R9
36 | Construction | Final test supporting document | 10 | 13;35 | 37 |  | R4: 2; R8: 2; R9: 1
37 | Construction | Operations manual | 10 | 36 | 38 |  | R3: 2; R4: 1; R8: 2; R9: 1
38 | Post-Contruction | Contracts closure | 20 | 37;4 | 39 |  | R3: 1; R4: 2; R7: 1; R10: 2; R11: 1; R12: 2
39 | Post-Contruction | Project closing report | 30 | 38 | 40 | bar: R7
40 | Post-Contruction | ACCEPTANCE Project 1 | 0 | 39

## Resources
ID | Name | Type | Units
R1 | Architect Sr | HC | 3
R2 | Architect Jr | HC | 5
R3 | Engineer Sr | HC | 2
R4 | Engineer Jr | HC | 4
R5 | PM 1 | HC | 1
R6 | PM 2 | HC | 1
R7 | PM 3 | HC | 1
R8 | Quality Manager Sr | HC | 2
R9 | Quality Manager Jr | HC | 1
R10 | Lawyer and Legal Specialist | HC | 2
R11 | Procurement Manager | HC | 1
R12 | Procurement Assistant | HC | 2