## Solution
Task Label | Task Name | Duration | Start Time | Finish Time | Predecessors | Successors
3 | Contract signing | 0 | 0 | 0 |  | 5
5 | Project planning | 60 | 0 | 60 | 3 | 6, 8
6 | Project execution and controlling | 516 | 60 | 576 | 5 | 44
8 | Documentation analysis | 30 | 60 | 90 | 5 | 9
9 | Consultation results report | 30 | 90 | 120 | 8 | 11, 12FC+5
11 | Architectural design | 20 | 120 | 140 | 9 | 13
12 | Lanscape design | 15 | 125 | 140 | 9FC+5 | 13
13 | Final design | 20 | 140 | 160 | 11, 12 | 15, 16, 17, 19FC+20, 20FC+35, 21
15 | Legal permits | 30 | 160 | 190 | 13 | 23
16 | Environmental permits | 30 | 160 | 190 | 13 | 23
17 | Construction license | 30 | 160 | 190 | 13 | 23
19 | Providers contracts | 45 | 180 | 225 | 13FC+20 | 24, 25, 27, 28, 30, 31, 33, 34, 35, 36
20 | Components contracts | 30 | 195 | 225 | 13FC+35 | 38, 39, 40
21 | Procurement documents | 70 | 160 | 230 | 13 | 23, 24, 25, 27, 28, 30, 31, 33, 34, 35, 36, 38, 39, 40
23 | Site preparation | 25 | 230 | 255 | 15, 16, 17, 21 | 24
24 | Sanitary Water system | 18 | 255 | 273 | 19, 21, 23 | 25
25 | Electrical system | 43 | 273 | 316 | 19, 21, 24 | 27, 28
27 | Soccer field | 36 | 316 | 352 | 19, 21, 25 | 28
28 | Changing rooms & toilettes | 39 | 352 | 391 | 19, 21, 25, 27 | 30
30 | Gym | 15 | 391 | 406 | 19, 21, 28 | 31
31 | Leisure area | 7 | 406 | 413 | 19, 21, 30 | 33
33 | Garden | 10 | 413 | 423 | 19, 21, 31 | 34, 38
34 | Roads | 10 | 423 | 433 | 19, 21, 33 | 35, 36, 38
35 | Decorative elements | 5 | 433 | 438 | 19, 21, 34 | 38
36 | Lagoon | 60 | 433 | 493 | 19, 21, 34 | 38
38 | Urban metallic components installment | 22 | 493 | 515 | 20, 21, 33, 34, 35, 36 | 39
39 | Soccer field and leisure zone components installment | 15 | 515 | 530 | 20, 21, 38 | 40
40 | Installation of water dispensers | 15 | 530 | 545 | 20, 21, 39 | 42
42 | Equipment functionality test | 15 | 545 | 560 | 40 | 43
43 | Final test supporting document | 10 | 560 | 570 | 42 | 44
44 | Operations manual | 5 | 576 | 581 | 43, 6 | 46
46 | Contracts closure | 3 | 581 | 584 | 44 | 47
47 | Project closing report | 1 | 584 | 585 | 46 | 48
48 | ACCEPTANCE Project 1 | 0 | 585 | 585 | 47

## Additional Info
Time
585