## P1
ID | Section | Name | Duration | Predecessors | Successors | R1 | R2
1 | CONTRACT SIGNING (0 DIAS) | Contract signing | 0 |  | 2;3;4
2 | PHASE 1 | Layout definition(VDR) | 80 | 1 | 5 | 1
3 |  | STRUCTURAL DESIGN | 80 | 1 | 5 | 1
4 |  | EQUIPMENT DESIGN | 80 | 1 | 5 | 1
5 |  | FINAL DESIGN REVIEW | 0 | 3;4;5

## Resources
ID | Name | Type | Units
R1 | Diseñador | HC | 1
R2 | Comprador | HC | 1